Republic of Marshall Islands

Ministry of Education, Sport and Training

RMI Education and Skills Strengthening Project

P171924

Negotiated

ENVIRONMENTAL and SOCIAL

COMMITMENT PLAN (ESCP)

December 2, 2020

ENVIRONMENTAL AND SOCIAL COMMITMENT PLAN

- The Government of the Republic of the Marshall Islands (hereinafter RMI or the Recipient) will implement the RMI Education and Skills Strengthening Project (the Project).  The RMI Ministry of Education, Sport and Training (MOEST) will lead and coordinate, with the involvement of the Ministry of Finance, National Training Council (NTC) and the Public School System (PSS). The International Development Association (hereinafter the Association) is providing financing for the Project.

- The Recipient will implement material measures and actions so that the Project is implemented in accordance with the Environmental and Social Standards (ESSs). This Environmental and Social Commitment Plan (ESCP) sets out material measures and actions, any specific documents or plans, as well as the timing for each of these.

- The Recipient, Ministries, NTC and PSS will also comply with the provisions of any other environmental and social documents required under the ESF and referred to in this ESCP, such as the Environmental and Social Management Plan (ESMP), Labor Management Procedures (LMP) and Stakeholder Engagement Plan (SEP), and the timelines specified in those documents.

- The Recipient is responsible for compliance with all requirements of the ESCP even when implementation of specific measures and actions is conducted by the Ministries and agencies referenced in 1. above.

- Implementation of the material measures and actions set out in this ESCP will be monitored and reported to the Association by the Recipient as required by the ESCP and the conditions of the legal agreement, and the Association will monitor and assess progress and completion of the material measures and actions throughout implementation of the Project.

- As agreed by the Association and the Recipient, this ESCP may be revised from time to time during Project implementation, to reflect adaptive management of Project changes and unforeseen circumstances or in response to assessment of Project performance conducted under the ESCP itself. In such circumstances, the Recipient or delegate(s) will agree to the changes with the Association and will update the ESCP to reflect such changes. Agreement on changes to the ESCP will be documented through the exchange of letters signed between the Association and the Recipient or delegate(s). The Recipient or delegate(s) will promptly disclose the updated ESCP.

- Where Project changes, unforeseen circumstances, or Project performance result in changes to the risks and impacts during Project implementation, the Recipient shall provide additional funds, if needed, to implement actions and measures to address such risks and impacts.

| MATERIAL MEASURES AND ACTIONS |  | TIMEFRAME | RESPONSIBILE ENTITY/AUTHORITY |
| --- | --- | --- | --- |
| MONITORING AND REPORTING |  |  |  |
| A | REGULAR REPORTING Prepare and submit to the Association regular monitoring reports on the environmental, social, health and safety (ESHS) performance of the Project, including but not limited to the implementation of the ESCP, status of preparation and implementation of E&S documents required under the ESCP, stakeholder engagement activities, functioning of the grievance mechanism(s). | Six monthly throughout Project implementation. | Ministry of Education to provide data and Ministry of Finance Department of International Development Assistance Central Implementation Unit to prepare and submit reports. |
| B | INCIDENTS AND ACCIDENTS Promptly notify the Association of any incident or accident related to the Project which has, or is likely to have, a significant adverse effect on the environment, the affected communities, the public or workers. Provide sufficient detail regarding the incident or accident, indicating immediate measures taken or that are planned to be taken to address it, and any information provided by any contractor and supervising entity, as appropriate. Subsequently, as per the Association’s request, prepare a report on the incident or accident and propose any measures to prevent its recurrence. | Minor incidents will be reflected in the six-monthly reports to the Association, serious incidents will be notified to the Association immediately (within 24 hrs). A report would be provided to the Association, as requested. | Ministry of Education to provide data and Ministry of Finance Department of International Development Assistance Central Implementation Unit to prepare and submit reports. |
| C | CONTRACTORS MONTHLY REPORTS Monthly reports on the Contractor’s implementation of environmental, health, safety and social safeguard measures will be submitted to the Association upon request. | On request. | Ministry of Education to provide contractors documents and Ministry of Finance Department of International Development Assistance Central Implementation Unit to submit reports to the Association. |
| ESS 1: ASSESSMENT AND MANAGEMENT OF ENVIRONMENTAL AND SOCIAL RISKS AND IMPACTS |  |  |  |
| 1.1 | ORGANIZATIONAL STRUCTURE The Project Implementation Unit will be led by a Project Manager (consultant) and supported by one Project Director from each of the NTC and PSS. Assessment and management of the environmental and social risks and impacts are delegated to the environmental and social staff of the Central Implementation Unit (CIU) who will provide operational support to the Project. The CIU staff will coordinate with the Project Manager, Project Directors and other key staff of the MOEST, NTC and PSS to manage environmental and social risks and impacts. CIU staff will include at least two individuals with responsibility for implementation, monitoring and reporting for relevant environmental and social aspects including but not limited to the Environmental and Social Management Plan, Labor Management Procedures and Stakeholder Engagement Plan. | At a minimum, one environmental specialist and one social specialist shall be maintained by the MOF DIDA CIU throughout Project implementation period. | Ministry of Education and MOF DIDA (CIU) |
| 1.2 | ENVIRONMENTAL AND SOCIAL ASSESSMENT Update, adopt, and implement, the Environmental and Social Management Plan that has been prepared for the Project, in a manner acceptable to the Association. | Throughout Project implementation. | MOF DIDA (CIU) on behalf of the PIU. |
| 1.4 | MANAGEMENT OF CONTRACTORS Incorporate the relevant aspects of the ESCP, including the relevant clauses from the Environmental and Social Management Plan, and the Labor Management Procedures, into the ESHS specifications of the procurement documents with contractors. Contractor to prepare a Contractor’s Environmental and Social Management Plan and Health and Safety Management Plan, commensurate with the project-specific risks, responding to the ESHS specifications in the bid documents. Thereafter ensure that the contractors comply with the ESHS specifications of their respective contracts. | Before launching the procurement process for relevant Project activities and thereafter through the carrying out of such activities. Contractor to submit the Contractors Environmental and Social Management Plan for review prior to works starting. | MOF DIDA (CIU) to prepare and disclose the instruments with PIU review and input. PIU and MOF DIDA (CIU) to adopt and implement instruments. MOF DIDA (CIU) to review Contractors Environmental and Social Management Plan, prior to works starting. |
| ESS 2: LABOR AND WORKING CONDITIONS |  |  |  |
| 2.1 | LABOR MANAGEMENT PROCEDURES Update, adopt, and implement the Labor Management Procedures (LMP) that have been developed for the Project. | Throughout Project implementation. | PIU and MOFA DIDA (CIU) |
| 2.2 | GRIEVANCE MECHANISM FOR PROJECT WORKERS Establish, maintain, and operate a grievance mechanism for Project workers, as described in the LMP and consistent with ESS2. | Grievance mechanism operational prior engaging Project workers and the procedures and grievance mechanism maintained throughout Project implementation. | PIU and MOFA DIDA (CIU) |
| 2.3 | OCCUPATIONAL HEALTH AND SAFETY (OHS) MEASURES Prepare, adopt, and implement occupational, health and safety (OHS) measures specified in the Environmental and Social Management Plan. | Throughout Project implementation | PIU to adopt and implement the OHS measures. MOF DIDA (CIU) to support the PIU and to prepare updates as required. |
| ESS 3: RESOURCE EFFICIENCY AND POLLUTION PREVENTION AND MANAGEMENT |  |  |  |
| 3.1 | WASTE MANAGEMENT PLAN: Contractors to prepare, adopt, and implement a Waste Management Plan in accordance with the measures specified in the Environmental and Social Management Plan. | Plan to be prepared prior to works starting. Plan to be implemented throughout period of construction. | Contractors to prepare, MOF DIDA (CIU) to review the plan and supervise the implementation. |
| 3.2 | RESOURCE EFFICIENCY AND POLLUTION PREVENTION AND MANAGEMENT: Resource efficiency and pollution prevention and management measures will be addressed in the design of building renovations and new buildings, in accordance with the measures specified in the Environmental and Social Management Plan. | During the period of design and prior to the finalization of tender documents or detailed design. | MOF DIDA (CIU) to review and supervise the design measures. |

| ESS 4: COMMUNITY HEALTH AND SAFETY |  |  |  |
| --- | --- | --- | --- |
| 4.2 | COMMUNITY HEALTH AND SAFETY: Prepare, adopt, and implement measures and action to assess and manage specific risks and impacts to the community, including school children, arising from Project activities, including, inter alia, construction or renovation of school buildings and imported labor in small communities, in accordance with the measures specified in the Environmental and Social Management Plan. | Preparation to occur prior to the start of activities that would create community health and safety risk. Implementation to occur throughout the activity phase. | Contractors to prepare and implement plans to manage risks under their control, with supervision from MOF DIDA (CIU). PIU to prepare and implement plans to manage risks under their control, with support from MOF DIDA (CIU). |
| 4.3 | GENDER-BASED VIOLENCE AND SEXUAL EXPLOITATION AND ABUSE RISKS: Prepare, adopt, and implement measures and action to assess and manage the risks of gender-based violence and sexual exploitation and abuse in accordance with the measures specified in the Environmental and Social Management Plan. | Preparation to occur prior to the start of activities that would create risk. Implementation to occur throughout the activity phase. | PIU with support from MOF DIDA (CIU) |

| ESS 5: LAND ACQUISITION, RESTRICTIONS ON LAND USE AND INVOLUNTARY RESETTLEMENT |  |  |  |
| --- | --- | --- | --- |
| 5.1 | LAND USE: Land requirements for the project will be screened to ensure that all land has valid leases in place and that the proposed activity is consistent with the purpose of the lease, in accordance with the measures specified in the Environmental and Social Management Plan. No land will be used for project purposes (such as building renovation or new buildings) unless the due diligence has been completed and suitable leases are in place. | Screening prior to any physical works activities. Due diligence to be completed prior to the approval for physical works to proceed. | PIU with support from MOF DIDA (CIU) |
| ESS 8: CULTURAL HERITAGE |  |  |  |
| 8.1 | CULTURAL HERITAGE MANAGEMENT: Cultural Heritage risks will be screened during design. If site specific mitigation is required, suitable measures shall be included in an update to the Environmental and Social Management Plan, for clearance by the Association. Contractor to adopt, and implement the chance finds procedure described in the ESMP. | Screening to occur during the design phase. Updates to the Environmental and Social Management Plan shall be completed and cleared by the Association prior to the tendering process. The chance finds procedure shall be implemented throughout the period of construction. | Screening to be completed by MOF DIDA (CIU). Updates to the Environmental and Social Management Plan shall be completed by MOF DIDA (CIU). Chance finds procedure and Environmental and Social Management Plan shall be implemented by the Contractor and supervised by MOF DIDA (CIU) |

| ESS 10: STAKEHOLDER ENGAGEMENT AND INFORMATION DISCLOSURE |  |  |  |
| --- | --- | --- | --- |
| 10.1 | STAKEHOLDER ENGAGEMENT PLAN PREPARATION AND IMPLEMENTATION Update, adopt, and implement Stakeholder Engagement Plan. | SEP operational 30 days after effectiveness. Implement throughout project implementation. The Stakeholder Engagement Plan shall be reviewed and updated at least annually, to reflect the needs of the Project work plan. | PIU and MOF DIDA (CIU) |
| 10.2 | PROJECT GRIEVANCE MECHANISM: Adopt, maintain and operate the grievance mechanism as described in the Stakeholder Engagement Plan. | As above. | PIU and MOF DIDA (CIU) to implement. MOF DIDA (CIU) to collect data and report. |
| CAPACITY SUPPORT (TRAINING) |  |  |  |
| CS1 | The PIU, project workers (such as consultants, contractors, NTC and PSS staff and training providers) to receive training on the World Bank Environmental and Social Framework and the requirements of the Project Environmental and Social Commitment Plan, Environmental and Social Management Plan, Labor Management Procedures and Stakeholder Engagement Plan: - Their roles and responsibilities for risk management under the Project - Implementing the LMP when engaging workers - Screening and managing risk - How to use the grievance mechanism - Stakeholder engagement basics for the Project - Code of conduct and Sexual exploitation and abuse and sexual harassment training for Project workers - Occupational health and safety relevant to their role - Civil works bid document preparation, contractor requirements and supervision | Within three months of the Effective Date and as required as new project workers are engaged on the project. | MOF DIDA (CIU) |