RMI Education and Skills Strengthening Project

ENVIRONMENTAL AND SOCIAL MANAGEMENT PLAN

NTC and PSS as Implementing Agencies supported by the Centralized Support Unit of the Division of International Development Assistance.

VERSION 4

12 October 2020

Republic of the Marshall Islands

Ministry of Education

World Bank Education and Skills Strengthening Project (P171924)

ENVIRONMENTAL AND SOCIAL MANAGEMENT PLAN

Quality Information

| Document name | Education and Skills Strengthening Project |
| --- | --- |
| Date | 12 October 2020 |
| Prepared by | G Venus and Collen Peacock, DIDA Safeguards Advisors |
| Reviewed | CIU, NTC, WB Task Team |

Version 4

TABLE OF CONTENTS

PREAMBLE	1

1.	BACKGROUND	2

2.	PROJECT DESCRIPTION	3

2.1.	Environmental and Social Risk Classification	4

2.1.1.	Risk Rating	4

2.1.2.	Environmental Risks	4

2.1.3.	Social Risks	5

2.1.4.	Stakeholder Engagement	6

3.	POLICY, LEGAL AND REGULATORY FRAMEWORK	6

3.1.	Introduction	6

3.2.	Country specific policy, legal and administrative frameworks relevant to the project	7

3.2.1.	Introduction	7

3.2.2.	General	7

3.2.3.	Environmental Legislation	7

3.2.4.	Labor Legislation	9

3.2.5.	Relevant International Conventions	9

3.3.	Applicable World Bank Environmental and Social Standards	10

3.3.1.	Environmental and Social Standards	10

3.3.2.	World Bank Group Environmental, Health and Safety (EHS) Guidelines	12

4.	ENVIRONMENTAL AND SOCIAL MANAGEMENT ROLES AND RESPONSIBILITIES	14

5.	PROJECT ACTIVITIES	15

6.	POTENTIAL ENVIRONMENT IMPACTS AND RISKS	19

6.1.	Asbestos Containing Material	19

6.2.	Lead-based paint residue	19

6.3.	Waste Management	20

6.4.	Water and Wastewater	20

6.5.	Vegetation Impacts	22

6.6.	Construction works Adjacent to Coastal Areas	22

6.7.	Traffic impacts and Impacts on Neighbors	23

6.8.	EPA Permits	23

6.9.	Source of Aggregate for Construction	23

7.	POTENTIAL SOCIAL IMPACTS, RISKS AND OPPORTUNITIES	23

7.1.	Ensuring Safety in Delivery of After-School Tutoring and Summer School Classes	23

7.2.	Ensuring Computing is Child-Safe	24

7.3.	Increasing Teacher and Counsellor Awareness and Responsiveness to Social Safeguards	24

7.4.	Reviewing Curriculum and Assessment Materials	25

7.5.	Constructing Training Facilities, Dormitories and NTC Facilities in Ebeye and Majuro	25

7.5.1.	Civil Works	25

7.5.2.	Construction of Dormitories	26

7.5.3.	Upgrading NTC’s facilities in Majuro and Ebeye	28

7.6.	Providing Stipends to Trainees, Childcare Services; and Subsidies to Interns	28

7.7.	Expanding the Role and Capacity of Counsellors	28

7.8.	Recognizing Prior Learning (RPL)	29

7.9.	Engaging with PIU Team Members	29

7.10.	Understanding Land Access	29

7.11.	Ensuring Health and Safety	29

7.11.1.	Community Health and Safety	29

7.11.2.	Student and Faculty Safety	30

7.11.3.	Construction-related occupational Health and Safety	30

8.	Civil Works Contractor - Environmental, Social, Health and Safety Clauses	31

8.1.	General – Preparation of Contractor’s Environmental and Social Management Plan	31

8.2.	Potential Asbestos Containing Material or Lead Paint	31

8.3.	Community and Worker Health and Safety	32

8.4.	Waste Management	32

8.5.	Prevention of Water and Air Pollution	33

8.6.	Preservation of Vegetation	33

8.7.	Construction Facilities	34

8.8.	Sourcing of Aggregates for Construction	34

8.9.	Worker Accommodation	34

8.10.	Worker Code of Conduct	34

8.11.	Cultural Heritage Chance Find Procedures	34

9.	STAKEHOLDER ENGAGEMENT	35

9.1.	Key Stakeholders	35

9.2.	Engagement during Development of Safeguards Instruments	35

9.3.	Engagement with community stakeholders during Construction Works	36

9.4.	Engagement of technical experts during Project preparation and inception	36

10.	GRIEVANCE MECHANISM	36

11.	BUDGET	36

12.	ANNEXES 	38

Annex 1: Abbreviations and Acronyms	39

Annex 2: Health and Safety Management Plan Guidelines	40

Annex 3: Risk Assessment Methodology	34

Annex 4: Stakeholder Engagement Plan	46

# PREAMBLE

This Environmental and Social Management Plan (ESMP) has been prepared for the Republic of the Marshall Islands (RMI), Education and Skills Strengthening Project (ESSP), pursuant to national regulations and the World Bank’s Environmental and Social Framework.

The ESMP addresses all project components and has been prepared for the entire project.  The ESMP provides a description of institutional arrangements, environmental and social risks, health and safety risks, mitigation, monitoring, and the management of Contractors.

Along with this ESMP, other environment and social instruments required under the Environmental and Social Framework have been prepared, including the Stakeholder Engagement Plan (SEP), Labor Management Procedure (LMP), and Environmental and Social Commitment Plan.

All instruments have been disclosed on the Ministry of Finance website www.rmi-mof.com/division-of-international-development-assistance/news-and-updates/ .

# BACKGROUND

The Government of the Republic of the Marshall Islands (GoRMI) is preparing the RMI Education and Skills Strengthening Project (ESSP, or the project) to increase equitable access to quality education and training programs focused on foundational and market-relevant skills development and to opportunities for continuing education, training, and employment in RMI and abroad.

While access and participation in elementary education in RMI is generally high, this drops considerably at secondary level and poor academic performance in elementary and secondary schools, especially the public ones, is a main concern. The poor quality of education at both elementary and secondary school levels impacts post-secondary studies and employment outcomes.

There are important equity and efficiency issues related to education for children and youth from neighboring islands. Technical and vocational education and training (TVET) options in RMI are both limited and fragmented. Better linking skills development with employment opportunities is needed for RMI to address the dual problem of high formal sector unemployment (especially among youth) and skills gaps. This ESMP has been developed to address these matters.

The Implementation Agency for the Project is the Ministry of Education, Sports and Training (MOEST) and the key focal agencies are the National Training Council (NTC) and the Public Schools System (PSS). Environmental and social instruments for the Project have been prepared by the Centralized Implementation Unit (CIU) of the Division of International Development Assistance (DIDA), under the RMI Ministry of Finance (MOF).

# PROJECT DESCRIPTION

The Project is structured around four components: the first and second components focus on improving the accessibility and quality of selected education and training programs offered in secondary schools, post-secondary institutions, and private training providers. The third component involves enhancing academic and career counselling and labor market intermediation services. The fourth component supports Project implementation and monitoring and evaluation. Within MOEST, the first component will be managed by PSS, the second and third by the NTC and the fourth jointly by NTC and PSS.

Subcomponent 1.3 (Equity in access to quality secondary education) includes construction and/or rehabilitation of secondary school dormitories and improvements in services, including food, supervision, learning and counselling support. Project development sites include: i) Majuro: College of the Marshall Islands (CMI) Arrak Campus, and Laura High School (Laura); ii) Ebeye: Gugeegue, Kwajalein Atoll High School, and the NTC facility; iii) Jaluit: Jaluit High School, and iv)Wotje: Northern High School.

The project is expected to bring about significant social and economic benefits by lifting the educational outcomes of young Marshallese to effectively engage and contribute to the workforce in RMI and abroad. The ESSP will also reduce gender gaps in TVET participation and increase the availability of technical skills in vulnerable outer island communities. Secondary benefits will accrue by reducing urban migration through expanding training and livelihood options in the outer islands, and by decreasing the need for the private sector to import skilled and semi-skilled workers.  It will also contribute to providing Marshallese migrating out of the country with better skills and preparation to enter the labor market of their new country.  Vulnerable neighboring island communities and gender gaps in participation and outcomes will be a specific focus of project design.

Project components, subcomponents and objectives are shown in the following table.

| Component 1 | Access to and quality of foundational and vocational secondary education Improve the acquisition of foundational skills (English and Math), market-relevant, and practical skills among secondary school students. This component also aims to promote improved access to learning in secondary schools by youth from outer islands. Support is organized around three subcomponents: |
| --- | --- |
| Subcomponent 1.1 | Foundational skills in secondary schools |
| Subcomponent 1.2 | Vocational and island life skills in secondary schools |
| Subcomponent 1.3 | Equity access to quality secondary education |
| Component 2 | Access to and quality of technical and vocational skills development Increase equitable access to quality and relevant technical and vocational education program leading to college-level certificate or diploma as well as shorter skills development programs. The support is organized around two subcomponents: |
| Subcomponent 2.1 | Design and delivery of market-relevant skills development programs |
| Subcomponent 2.2 | Equitable access to TVET training and skills development programs |
| Component 3 | Strengthening the institutions for workforce development Strengthen workforce planning, skills recognition, and employment services with a view to improving labor market outcomes for Marshallese at home and abroad. The support is organized around four subcomponents: |
| Subcomponent 3.1 | Improved labor market information |
| Subcomponent 3.2 | Career counselling and job matching services |
| Subcomponent 3.3 | Recognition of Prior Learning |
| Subcomponent 3.4 | Work placement and internship program |
| Component 4 | Project Implementation Support, Planning, Capacity Building, and Monitoring and Evaluation Support implementation and monitoring and evaluation. Under this component, the project will finance long-term consultants (including one project manager, two component coordinators, one program assistant); short-term consultancy services to provide technical assistance on preparing for the end of the Compact and on communication strategies; and supplies including transport, travel, meetings, operating expenses |

## Environmental and Social Risk Classification

### Risk Rating

According to the Concept Environmental and Social Review Summary (ESRS), the ESSP has a Moderate Environmental and Social Risk Rating. This rating was assessed based on the Project not being large or complex; not involving activities with high potential to harm people or the environment; site locations not being in environmentally or socially sensitive areas, and the low magnitude and predictable nature of risks, which can be easily mitigated through specified mitigation measures. There are also no significant concerns related to the Borrower experience, track record, or ability for effective stakeholder engagement, and no significant contextual risks.

The risk ratings identified in the ESRS have been validated based on the mitigation measures set out in this ESMP which has given particular consideration to (ii) management of waste and to sourcing sustainable building materials and aggregates which are often challenging issues in neighboring islands such as Wotje and Jaluit; and (ii) integrating the mitigation of social harm and maximizing benefits into project design.

### Environmental Risks

Environmental risks are identified in the ESRS as Moderate and relate primarily to managing construction impacts during renovations and development of new buildings, and managing water use, wastewater and solid waste from the upgraded facilities. Risks also relate to resource use and waste that may come from vocational training. This ESMP includes tools to identify and manage these risks using Good International Industry Practice.

Risks relating to non-physical works are considered Low.

### Social Risks

The project is expected to bring about significant social and economic benefits by lifting the educational outcomes of young Marshallese to effectively engage and contribute to the workforce in RMI and abroad. The ESSP will also reduce gender gaps in TVET participation and increase the availability of technical skills in vulnerable outer island communities. Secondary benefits will accrue by reducing urban migration through expanding training and livelihood options in the outer islands, and by decreasing the need for the private sector to import skilled and semi-skilled workers.  It will also contribute to providing Marshallese migrating out of the country with better skills and preparation to enter the labor market of their new country.  Vulnerable neighboring island communities and gender gaps in participation and outcomes will be a specific focus of Project design.

Support for vulnerable groups are integrated into the project activities and activities are tailored to achieve inclusion of girls and outer island children who are without family support. These include provision of dormitories that exclusively target local youth and are located within their home communities to encourage attendance in safe learning spaces. Child protection measures are also built into the design of the operation include training of counsellors in all public schools  to support students and staff.

The primary social risks to beneficiaries (including students, teachers and schools) during project works include: i) potential disruptions to learning caused by noise and air-borne pollutants and/or reduced access to classrooms if works are undertaken when schools are operational; ii) potential health and safety issues caused by unsafe work practices and/or uncontrolled access to construction sites, and iii) potential for sexual exploitation, abuse and sexual harassment (SEAH) by  project workers.

These risks are assessed as moderate and can be readily managed through proactive and ongoing attention to the following mitigation measures: by

- Ensuring project works are undertaken during semester breaks or at other times that students are off-site;

- Securing off-site temporary classroom space if necessary;

- Ensuring construction areas remain inaccessible to unauthorized persons and that proper safety procedures are followed;

- Ensuring transport logistics are developed in consultation with school management and local authorities to ensure safe passage and access;

- Developing and enforcing site-specific codes of practice governing all physical works;

- Ensuring all project workers sign codes of conduct and receive awareness training

- Providing awareness training for students, parents and school personnel;

- Consulting with SEAH and other social welfare service providers, in each location, to ensure referral protocols are in place and support is available should this be required;

- Ensuring “alert” systems, and grievance redress mechanisms in place and understood by all parties, and

- Ensuring that workers are trained and properly supervised.

The risk of sexual exploitation and abuse/sexual harassment (SEA/SH) is assessed as ‘low’ given the confined nature, relatively small number of construction workers from outside the community and limiting works taking place while students are in school, it is acknowledged as a prevalent contextual risk within local communities. Gender-based violence, including all forms of physical, sexual and psychological abuse, is seriously entrenched in RMI society which exacerbates SEAH concerns. As such, a range of mitigation measures will be used including worker training; codes of conduct; supervision protocols; awareness workshops for school personnel and students, and alert mechanisms. SEAH service providers are available in RMI and will be consulted during project preparation to ensure support arrangements are in place and aligned with WB guidelines for addressing SEAH in investment projects.

In addition to social risks associated with project construction, there is also potential for SEAH related to the physical design and security arrangements of new/renovated educational and boarding facilities. As outlined in Section 7.5.2, this risk will be mitigated by ensuring design options fully consider security and privacy issues and take into account community practices and cultural perspectives.

While social risks related to non-physical works are moderate, the project can play an important role in raising awareness of key stakeholders, including school personnel, students and parents on social protection issues, prevention, and response.

### Stakeholder Engagement

Stakeholder consultation will focus on ensuring beneficiaries are actively engaged in identifying potential social and environmental issues and solutions, as well as potential value-add options to maximize project benefits. This could include opportunities to collaborate with existing service providers to expand reach and effectiveness of planned activities. Information on specific project stakeholders, engagement strategies, objectives and responsibilities are identified in the SEP.

### Environmental and Social management documentation

In order to manage project risks, this document (ESMP) provides an analysis of project impacts and identifies appropriate mitigation measures, including who is responsible for implementation.  As noted above, a separate stakeholder engagement plan has also been prepared which outline how the project will ensure affected and interested parties will receive information and be consulted throughout the life of the Project.  A labor management procedures (LMP) addressed labor risks and defines Project working conditions.   Finally, a Environmental and Social Commitment Plan (ESCP) is referenced in the legal agreement between the Bank and the Borrower, and defines key actions and responsibilities for Project implementation.

# POLICY, LEGAL AND REGULATORY FRAMEWORK

## Introduction

This section describes the following:

- Country specific policy, legal and administrative frameworks relevant to the project;

- World Bank environmental and social standards (ESS) relevant to the project;

- World Bank Group Environmental, Health and Safety Guidelines (EHS Guidelines) relevant to the project; and

- Other relevant international and regional conventions that are adopted by the Borrower, such as Stockholm Convention for Persistent Organic Pollutants, Basel Convention for hazardous wastes and disposal.

## Country specific policy, legal and administrative frameworks relevant to the project

### Introduction

The Government of the Republic of Marshall Islands operates under a mixed parliamentary-presidential system as set forth in its Constitution. Elections are held every four years, with each of the twenty-four constituencies electing one or more representatives (senators) to the lower house of RMI's uni-cameral legislature, the Nitijela. The President, who is head of state as well as head of government, is elected by the 33 senators of the Nitijela.

Legislative power lies with the Nitijela. The upper house of Parliament, called the Council of Iroij, is an advisory body comprising twelve traditional leaders. The executive branch consists of the President and the Presidential Cabinet, which consists of ten ministers appointed by the President with the approval of the Nitijela. The twenty-four electoral districts into which the country is divided correspond to the inhabited islands and atolls.

Article II of the Constitution contains a Bill of Rights which outlines the basic rights afforded to people in the Marshall Islands. These rights include equal protection to men and women and freedom from discrimination, personal autonomy and privacy, access to health education and legal services, ethical government and other rights retained by the people.

### General

RMI Constitution: The Constitution of the Republic of the Marshall Islands mandates the government of the RMI to be responsible to safeguard and maintain heritage and ensure that the islands can continue to provide a home to the people of the Marshall Islands for generations to come.

Local Government Act 1980: An Act providing the manner of operation of the system of local government. Each atoll has its own local Council.

Industries Development Act: The NTC was established in 1991 under the amended Industries Development Act (P.L. 1991-140) to serve as “the lead agency in coordinating, regulating, and promulgating policy on vocational and job training programs in the RMI”. This legislation has been amended three times, in 2000 (P.L. 2000-21), in 2005 (P.L. 2005-39), and in 2015 (P.L. 2015-47). The 2015 amendment updated and reinterpreted the Council’s mandate to include functions one through eleven as listed below. Function 12 will be added under the Rights of Persons with Disabilities (Consequential Amendments) Bill 2018.

### Environmental Legislation

National Environmental Protection Act 1984 (NEPA): An Act to provide for the establishment of a National Environmental Protection Authority (EPA), and for the protection and management of the environment. Marshall Islands environmental impact assessment legislation is found largely in Part IV. The NEPA Act 1984 is supported and further elaborated in a set of eight regulations for protection of surface and marine waters, and air quality, and managing of potential impacts from earth works, sanitation systems, waste, and new infrastructure development. The Act and these regulations, along with the Coast Conservation Act 2008, provides the framework for the protection of resources and environmentally sustainable development in RMI. The 1994 Environmental Impact Assessment Regulations (Regulations) promulgated by the RMI EPA provide project proponents specific details for the environmental impact assessment processes.

The most relevant national regulations for this project include: Environmental Impact Assessment Regulation 1994, the Solid Waste Regulations 1989 and the Toilet Facilities and Sewage Disposal Regulations 1990.

Environmental Impact Assessment (EIA) Regulation 1994: The central environmental planning legislation in RMI aims to ensure that environmental concerns are given appropriate consideration in decision-making for any new infrastructure project. The EIA regulation requires a preliminary proposal for every development activity and applies a two-step assessment process to determine the level of assessment required. For projects involving earthmoving, the development proposal is submitted to the RMI EPA via a Major or Minor Earthmoving Permit Application. It is reviewed through an internal RMI EPA Preliminary Environmental Assessment (PEA) process.  This process will apply to Project construction works.

Step 1 is an initial evaluation of the PEA to determine if the activity has the potential for significant effect on the environment.

Step 2 is either the issuance of an Earthmoving Permit with conditions (e.g. Minor and some Major applications), or a requirement for an EIA for proposals (e.g. Major applications) assessed to have potential significant impact which will be reviewed and form the basis of an approved decision with conditions, or a not-approved decision.

Conditions pre- or post-EIA may include a requirement for an Environmental Management Plan (EMP). In cases where a proponent ESMP has been drafted prior to the submission of an Earthmoving Permit Application, it may require modification to meet the conditions of approval.

Solid Waste Regulations 1989: The purpose of these regulations is to establish minimum standards governing the design, construction, operation and maintenance of solid waste storage, collection, and disposal systems. The Regulations cover the management of bulky waste such as appliances, tree branches or other oversize waste such as interior building cladding. The Regulations also define hazardous waste as any waste or combination of wastes which pose a substantial present or potential hazard to human health or living organisms because such wastes are non-degradable, or persistent in nature, or because they can be lethal, or because they may otherwise cause or tend to cause detrimental cumulative effects. The Regulations list the general requirements for the storage of solid waste as well as detailing the type of containers that may be used to store solid waste. The Regulations also govern the handling of hazardous waste within RMI.  The project is not anticipated to generate hazardous wastes.

Toilet Facilities and Sewage Disposal Regulations 1990: Was promulgated by the RMI EPA with the approval of the Minister of Health and Human Services pursuant to Section 21 of the NEPA.  The purpose of the Toilet Facilities and Sewage Disposal Regulations 1990 is to establish minimum standards for toilet facilities and sewage disposal to minimize environmental pollution, health hazards, and public nuisance from such facilities.

### Labor Legislation

Labor (Non-Resident Workers) Act 2006:  Sets out various requirements of workers including the need to hold work visas by foreign (other than United States of America) contractors and workers including fly-in fly-out consultants who are restricted by the 30-day entry visa limit.  No other Labor Legislation constraints apply to workers potentially engaged on project activities.

Public Service Commission Act 1979: Established the Public Service Commission (PSC) which is the employing authority of the government charged with the responsibility for developing, coordinating, regulating, and administering all personnel matters relating to and affecting the Public Service.  Some statutory agencies whose personnel administrations are governed by their respective Board of Directors do not fall under PSC, including: National Telecommunications Authority, Marshall Islands Marine Resources Authority, Public Safety, RMI EPA, RMI Scholarship, Loan, and Grant Board, RMI Shipping Authority, Marshall Energy Company, RMI Seaport and Airport Authority.

There is no Occupational Health and Safety (OHS) legislation in RMI.

### Relevant International Conventions

| Stockholm Convention for Persistent Organic Pollutants | Purpose of the Stockholm Convention is to protect human health and the environment from Persistent Organic Pollutants. RMI became a Party to the Convention on 27 January 2003 and the Convention entered into force globally on 17 May 2004. |
| --- | --- |
| Basel Convention for hazardous wastes and disposal; and | Basel Convention is an international treaty that is designed to ensure the safety of the environment by reduction of transport of hazardous waste between nations, such as from more to less developed countries. RMI became a Party to the Convention on 27 January 2003 and the Convention entered into force on 27 April 2003. |
| Convention on the Elimination of All Forms of Discrimination Against Women (CEDAW) | RMI ratified the Convention on the Elimination of All Forms of Discrimination Against Women (CEDAW) on 2nd March 2006, wherein RMI made a commitment to ensure that the principles for equality are adhered to and that discriminatory practices including SEAH are abolished. |
| Convention on the Rights of the Child (CRC) | RMI ratified the CRC in Oct. 1993, a human rights treaty that sets out the civil, political, economic, social, health and cultural rights of children, defined as someone under the age of eighteen. On 29 Jan 2019, the GoRMI signed the optional protocol to the CRC on the sale of children, child prostitution and child pornography. |
| Convention on the Rights of Persons with Disabilities (CRPD) | RMI ratified the CRPD on 17 March 2015 and passed the Rights of Persons with Disabilities Act which commit the GoRMI to protect the rights and dignity of persons with disabilities. Of relevance to the ESSP are CRPD provisions on inclusive education and accessible infrastructure. |

## Applicable World Bank Environmental and Social Standards

### Environmental and Social Standards

Using the WB ESS, project risks are classified as Moderate, with five of the ten standards screened as relevant.

The screening of social risks and impacts is based on discussions with project implementing and focal agencies (MOEST, PSS and NTC), and other relevant stakeholders including the Ministry of Works, Infrastructure, and Utilities (MWIU), and the Ministry of Health and Human Services. ESS screening also took into account national legal and policy requirements related to the environment and social environment, and the application of various protocols such as infectious disease control and medical waste management.

ESS #5 to #9 are assessed as not relevant to the project; mitigation measures to address the relevant standards are shown in the following table.

| Required Project Environmental and Social Standard Actions |  |
| --- | --- |
| Environmental and Social Standards | Required Measures and Actions |
| ESS1 Assessment and Management of Environmental and Social Risks and Impacts | CIU will support the management of environment, social, heath and safety risks and impacts of the project including mobilization of environmental and social risk management specialists if necessary. The ESMP provides guidance with respect to management of ESS1. |
| ESS2 Labor and Working Conditions | An LMP has been prepared. A Labor Grievance Mechanism (refer to the LMP) has been prepared which includes provisions to prevent SEAH, gender-based violence (GBV) and/or violence against children in the workplace, to be adopted and applied under the project. OHS management is included in this ESMP. |
| ESS3 Resource Efficiency and Pollution Prevention and Management | ESS3 is relevant to the project. Aggregates will be required for construction purposes. There are no identified sustainable local sources of aggregates in RMI; sand and rock are mined from foreshore areas. Construction building waste will be produced and, due to a lack of sanitary landfills in RMI, will need to be recycled or reused locally or exported for recycling or authorized disposal. Hazardous waste (asbestos and lead-based paint residue from construction) will also be considered at the design phase of building renovation and appropriate mitigation will be included in the contractors bid documents and the contractor’s ESMP. This ESMP sets out mitigation measures for aggregates, water, wastewater and waste management and focusses on specificities of sites as appropriate. |
| ESS4 Community Health and Safety | Although ESS4 is relevant to the project, the ESMP concluded that risks from community health and safety from construction activities are minor and manageable. Works will be contained within school precincts and the public can easily be excluded; specific mitigation has been put in place to ensure student safety if any construction works are undertaken during terms, however all efforts will be taken to ensure this does not occur. The Contractors may bring in workers from off-island and while the numbers are not expected to be significant they may be resident for some time on small islands (Jaluit, Wotje) and working in close proximity to school children, depending on the timing of works. The ESMP also includes an assessment of associated risks relating to harassment of children and safety risks for children arising from imported labor; and identifies suitable management measures and mitigation. |
| ESS5 Land Acquisition, Restrictions on Land Use and Involuntary Resettlement | ESS5 is not relevant for the project. Land will be required to renovate, construct and operate facilities and school accommodation. The scale or extent of physical works ranges from small scale renovations to 1 or 2 story extensions/new builds depending on need. Buildings or renovations will be located on school or tertiary education precincts on Government-leased land. The DOFA CIU Safeguards Advisors have completed due diligence on land access issues and confirmed no additional land access instrument is required. All land for project works is either PSS school leasehold land, CMI leased land or NTC leased land. Project-related activities are consistent with the provisions of existing leases and activities pose no additional requirements in terms of land tenure/ownership. No private land is required and no human resettlement is required. Management of works, including timing and segregation from non- work sites will be managed under ESS1; appropriate mitigation has been included in the ESMP. |
| ESS6 Biodiversity Conservation and Sustainable Management of Living Natural Resources | ESS6 is not relevant. Buildings or renovations will be within school or tertiary education precincts on Government-leased land. These areas are highly modified and do not have any natural values. Technical advisory relates to improving the education sector and TVET outcomes, with no specific relevance to biodiversity conservation and sustainable management of living natural resources. |
| ESS7 Indigenous Peoples/Sub-Saharan African Historically Underserved Traditional Local Communities | ESS7 is not relevant. |
| ESS8 Cultural Heritage | ESS8 is not relevant to the project. Buildings or renovations will be within school or tertiary education precincts on Government-leased land. These precincts may include cultural heritage structures or artifacts such as churches, chapels, graves or World War II relics. No obvious cultural heritage artifacts are apparent at each site. Chance find procedures have been included in the ESMP. Technical advisory relates to improving outcomes, with no specific relevance to tangible or intangible heritage. |
| ESS9 Financial Intermediaries | ESS9 is not relevant. |
| ESS10 Stakeholder Engagement and Information Disclosure | An SEP and Project Grievance Mechanism (GM) have been prepared as set out in this ESMP. The GM will be made publicly available to receive and facilitate resolution of concerns and grievances in relation to the project, consistent with ESS10. |

### World Bank Group Environmental, Health and Safety Guidelines

The World Bank Group’s EHS Guidelines represent good international practice for managing environmental, social, and community/occupational health and safety risks in project design and implementation. EHS Guidelines also outline performance levels and measures for facility development, construction and decommissioning and use of latest technologies at reasonable cost.

#### General EHS Guidelines

- Environmental

The General Environmental EHS Guideline provides methods and approaches for the management of wastewater, noise and dust during construction, water conservation and solid waste management.

2.0 Occupational Health and Safety

The fundamental premise for OHS under the EHS Guidelines is that “Employers and supervisors are obliged to implement all reasonable precautions to protect the health and safety of workers” and that “Companies should hire contractors that have the technical capability to manage the occupational health and safety issues of their employee”.

The EHS Guidelines also require that prevention and control measures to minimize occupational hazards should be based on comprehensive job safety analyses (JSA). Annex 2 contains a Health and Safety Management Plan Guideline which incorporates a basic JSA methodology. The CIU Safeguards Advisor will assist the contractor in undertaking the JSA and preparing its Health and Safety Management Plan.  The principles are:

•	Eliminating the hazard by removing the activity from the work process. Examples include substitution with less hazardous chemicals, using different manufacturing processes, etc.;

•	Controlling the hazard at its source through use of engineering controls. Examples include local exhaust ventilation, isolation rooms, machine guarding, acoustic insulating, etc.;

•	Minimizing the hazard through design of safe work systems and administrative or institutional control measures. Examples include job rotation, training safe work procedures, lock-out and tag-out, workplace monitoring, limiting exposure or work duration, etc.; and

•	Providing appropriate personal protective equipment (PPE) in conjunction with training, use, and maintenance of the PPE.

- Community Health and Safety

This guideline provides approaches and methods for drinking water quality, life and fire safety for building design and structural design of buildings.  Some guidance may be useful for new building construction and renovation, relating to traffic safety (transport of materials) and communicable disease control from imported labor.

4.0 Construction and Decommissioning

The Construction and Decommissioning EHS Guideline provides guidance for specific community and occupational health and safety and environmental issues relating to new buildings or building renovation.

#### Environmental, Health and Safety Guidelines for Water and Sanitation

This guideline provides guidance for new and upgraded water supply and sanitation at various scales and is relevant for school building upgrades and new school buildings.

# ENVIRONMENTAL AND SOCIAL MANAGEMENT ROLES AND RESPONSIBILITIES

Three main bodies will constitute the governance arrangements under the project:

The Project Steering Committee will be established to oversee project implementation and provide strategic guidance. The Project Steering Committee will ensure coordination among stakeholder ministries (including MOEST and MOF), employer representatives and non-government training providers), and provide a platform for regular sharing of information and reporting on project progress. It will be comprised of representatives from the MOF, PSS, NTC, the University of the South Pacific (USP), CMI, the Division of Labor (Ministry of Justice), the PSC, the Ministry of Culture and Internal Affairs, the RMI Chamber of Commerce and non-governmental organizations.

The MOEST has indicated its plan to establish a Secretariat Office within the Ministry. Once this has been done, the Secretary will chair the Project Steering Committee. Until then, the Project Steering Committee will be chaired by the Minister of MOEST. The Project Steering Committee will be established within three months of the effective date of the Financing Agreement. From a environmental and social risk management perspective, the Project Steering Committee will provide strategic guidance and decisions for the implementation of the Project.

The Project Implementation Unit (PIU), to be housed within the NTC, will have responsibility for the day-to-day operations and supervision of project consultants and contractors. The PIU will include civil servants to maximize government buy-in and build management capacity. NTC and PSS will each nominate one Project Director at Deputy Commissioner/Manager level from among existing  civil servant staff to lead the work, with support from  four consultants: one Project Manager, two Component Coordinators (one for component 1 and one for components 2 and 3), and one Administration Assistant. To ensure adequate coordination across components and activities, PIU consultants and contractors will be based together within NTC’s offices (when more sufficient space is available), while the Component 1 coordinator will regularly check-in with the PSS and work closely with the PSS Project Director.

- Construction works will be undertaken by Contractors engaged by the PSS, under the oversight of the Project Management Unit (PMU) of the MWIU based in Majuro.

- Management of School Repair and Refurbishment works will be led by the Assistant Secretary, School Facilities, Public School System, MOEST, based in Majuro.

- Quality Inspections of School Repair and Refurbishment works will be led by the Manager of the MWIU PMU, based in Majuro.

The CIU, housed within DIDA in the MoF will provide procurement and financial management support to the project. In addition, the CIU Environmental and Social Safeguards Advisors will: i) provide technical assistance and oversight to the PIU for environmental and social safeguards requirements as per their terms of reference; ii) provide oversight of contractor environmental and social performance, and iii) be responsible for oversight of the project grievance redress mechanism.

# PROJECT ACTIVITIES

The ESSP includes the following activities all of which are addressed in this ESMP:

- Development of curricula, assessments and revised training programs including the production of guidelines and training material (printing);

- Development of human rights, cultural affirmation and traditional skills curriculum;

- Compensation for teachers and college students delivering after-school tutoring and summer school classes;

- Provision of stipends to trainees enrolled in short skills development programs;

- Payment of subsidies to the wages of individuals selected for participation in the work placement program;

- Supply of childcare services to encourage female participation ;

- Procurement of computers and equipment;

- Training delivery to teachers and principals and providing additional teaching support;

- Design, construction or renovation of educational facilities and dormitories, and operation of those buildings;

- Grants to training providers to develop and deliver TVET course;

- Procurement and maintenance of equipment, which may have waste or hazardous materials to manage;

- Recruitment of staff to manage and implement the project;

- Revise/expand the role of counsellors to include a greater emphasis on continuing education, employment and career pathways.

Activities will be undertaken at the following sites. Figures 1 to 6 provide aerial depictions.

- Majuro – CMI Arrak Campus:

The CMI Arrak facility will involve construction of a new dormitory facility on CMI leasehold land, ocean-side and across the road from the CMI Arrak campus. The construction site will be located within 30m of the ocean-side high tide level and will potentially be subject to inundation during future elevated sea levels.  Design should incorporate climate resilient features.  Also given the Arrak construction site is not within the existing campus footprint, it may be accessible to the general public. As such, attention will be needed to ensure security and public/community safety.

- Majuro - Laura High School: Dormitory renovations.

- Ebeye – Gugeegue – Kwajalein Atoll High School – Dormitory renovations.

- Ebeye- NTC facility – Dormitory renovations.

- Jaluit – Jaluit High School – Dormitory renovations.

- Wotje – Northern High School – Dormitory renovations.

Depending on facility and the needs of the school, the renovations and / or new buildings may include any of the following:

- Improved or new potable and non-potable water supply (roof top collection);

- Energy generation (i.e. roof top solar panels) or the structural design to allow for panels at a later date;

- Septic tanks or connection to reticulated systems for domestic wastewater treatment and disposal; and

- Trade waste treatment and disposal upgrades for commercial-type wastewater from training facilities (automotive or small engine training);

Figure 1: CMI Campus, Arrak, Majuro

Figure 2: Laura High School, Laura, Majuro

Figure 3: Kwajelein Atoll High School, Gugeegue, Kwajalein

Figure 4: Jaluit High School, Jaluit

Figure 5: Northern High School, Wotje

Figure 6: NTC Facility, Ebeye

# POTENTIAL ENVIRONMENT IMPACTS, RISKS AND MITIGATION MEASURES

This section describes the potential impacts of the project on the physical and human environment. It is noted that all information is derived from existing sources and discussions as no field investigations were able to be undertaken due to Covid-19 related travel restrictions.  However, the authors have previously visited the project sites in relation to other projects and the conclusions are considered valid in this context. The majority of potential impacts are associated with the construction phase of the project, noting that no large demolition works are expected.

Key areas of potential risk are discussed separately in the following sections.

## Asbestos Containing Material

Asbestos containing material in this context refers to existing building elements (e.g. wall sheeting, roof sheeting, pipework, insulation etc.) that may contain asbestos. When products containing asbestos are damaged or wear down over time, small fibres are released and become airborne. Breathing in asbestos fibres can cause a range of diseases including cancer.

Secretariat of the Pacific Regional Environment Programme (SPREP) undertook an RMI asbestos survey across Majuro in 2014 which found very little indicative presence of asbestos in residential, commercial and government buildings.

It is therefore considered that there is a low likelihood of asbestos being encountered at any of the project construction / physical works sites.  However, anecdotally, the United States of America military provided trailers previously located at Kwajalein Atoll High School, Gugeegue have been linked to the presence of asbestos, and that high school is old enough to potentially have asbestos.  In addition, the SPREP study did not cover other neighboring islands.  Therefore a suitable screening and response is required to be carried out by facility designers, prior to any work by Contractors.

Facility designers will screen for asbestos containing materials during early site visits.  Where potential materials are identified, samples shall be taken and sent to a laboratory for analysis of asbestos content.  Where tests are positive, an asbestos removal plan will be prepared, which will include risk of exposure to workers and building occupiers/users and measures to avoid exposure.  The RMI EPA will be notified in relation to the management of hazardous waste.  The Contractor bid documents will be clear about the requirements to manage asbestos in accordance with the removal plan, including: engagement of a specialist sub-contractor with experience in asbestos removal to remove materials prior to demolition or renovation starting.  The subcontractor will be equipped with the appropriate PPE and handling and storage equipment.  Project managers, site supervisors and other personnel will be required to undergo training prior to entering the site while asbestos is present; all other staff, students, workers and sub-contractors will not be able to enter the site until the asbestos is removed.  Asbestos containing material will be contained, labelled, removed and disposed at a suitable offshore facility.

## Lead-based paint residue

Older buildings are likely to contain lead-based paint.  Lead is a highly poisonous metal affecting almost every organ in the body. Of all the organs, the nervous system is the mostly affected target in lead toxicity, both in children and adults. The toxicity in children is however of a greater impact than in adults.

Building renovations and demolition activities generate dust that may include lead from interior and exterior lead-based paint.  This lead dust eventually falls and settles on surfaces.

Construction workers can inhale this lead dust and also track the lead dust to their homes and nearby communities.  Through inhalation and tracking, construction workers, their families and communities, can be exposed to the hazardous effects of lead.

Most buildings constructed prior to 1980 will have lead paint somewhere within them.  One of the most straightforward ways of determining if lead paint is present is to scrape down to the bare surface of a wall, either the drywall, plaster, or panelling. If the sub-surface appears to only have one or two coats of paint on it, there is a high probability that the paint isn't lead-based.  As an alternative, an inexpensive test kit is available.

The Kwajalein Atoll high School at Gugeegue is understood to be older than 40 years and could potentially have lead paint residues which might be disturbed during renovation works.  The age of buildings on Wotje and Jaluit are reported to be younger (no more than 10 years old) having been funded by way of Japanese development assistance.  The likelihood of lead-based paints here and on Majuro is considered low.  Nevertheless, facility designers will screen for lead-based paint, test if screening identifies a potential risk, and a containment and removal plan prepared for the Contractor’s bid documents.

## Waste Management

Based on experience with similar construction activities in RMI, quantities of waste generated from construction activities are likely to be low, principally as a consequence of the costs of materials. However, building renovations might require disposal of demolition wastes which could potentially pose a risk at all sites facilities given very limited waste disposal options.  On Jaluit and Wotje, waste disposal facilities are rudimentary, comprising dumps adjacent to the roadside (Jaluit) or at the end of the airport (Wotje).  Ebeye and Majuro landfills are managed facilities, but both are space-limited.

Accordingly, any demolition wastes associated with the project will need to be recycled or reused, as is the usual practice with construction activities in RMI.

No hazardous waste is anticipated, with the exception of potential asbestos/lead-based paint waste.  If these or other hazardous wastes are generated, including paint containers and glue, the protocol for disposal of lead-based paint will apply.

All solid waste material generated by the project will need to be recycled or reused locally or will need to be exported for recycling or for appropriate and authorised overseas disposal.

Specific waste mitigation options include:

- Design to minimise waste generation by selecting suitable materials, construction methodologies for the RMI conditions.

- Capacity building of contractors by supervision engineer where necessary to improve resource efficiency on the building site.

- Contractor ensures all construction waste is recycled or re-used as far as practicable at all construction locations.

- Contractor manages all residual waste in accordance with the relevant provisions of Solid Waste Regulations 1989 including requirements for the storage of solid waste such as type of containers.

- All residual waste from Wotje, Jaluit and Ebeye taken back to Majuro to be further recycled or re-used on Majuro if practicable or exported from RMI to an authorized recycling or disposal location.

- Contractor to provide evidence of satisfactory waste management and disposal (e.g. receipts).

## Water and Wastewater

Water for general use by facilities (washing) and drinking water will be sourced from existing rainwater catchments, which PSS advise are sufficient to accommodate anticipated activities (which are not water -intensive activities).  Water for making concrete will be sourced from the same supply.  The volumes required will be met by available supply.

Wastewater will be disposed of either jointly with existing wastewater or solo to septic tanks.  The required operational volumes are considered appropriate to be accommodated by existing water sources and disposal systems at each facility.  Facilities are reported to currently have over-capacity in terms of water availability from rainwater supply.

However, the northern islands may be subject to drought which could affect overall water supplies. Each facility will need to develop a water contingency plan for drought situations.

Existing septic tank systems will be used for domestic wastewater.  PSS advises that existing facilities at Wotje and Gugeegue are adequate and will be sufficient to accommodate domestic wastewater from renovated buildings.  The Jaluit renovation and the new construction at Arrak, Majuro will require new septic tanks which will be installed in accordance with EPA administered Toilet Facilities and Sewage Disposal Regulations 1990.

Toilet Facilities and Sewage Disposal Regulations require that toilet/septic tank systems involving discharge to a private septic tank MUST NOT:

- Locate, construct or maintain a septic tank or seepage pit so as to contaminate any potable water supply.

- Locate a septic tank or seepage pit at a horizontal distance of less than 15 feet from any body of water.

- Locate a septic tank or seepage pit less than 100 feet from any well, without the written permission of the RMI EPA.

- Allow for liquid depth which is less than thirty inches and more than seventy-two inches.

- Put a structure or obstruction near the tank that will interfere with accessibility.

- Place a cover over any septic tank system or seepage pit before it has been inspected and approved by the RMI EPA or its authorized representative.

These regulations also specify that construction of Septic Tank systems MUST:

- Make a hole large enough to permit the proper placement of the tank and backfill.

- Place the tank on a solid base that will not settle and will be level.

- Construct a septic tank that is sound, durable, and made of watertight materials that are not subject to excessive corrosion or decay.

- Design the septic tank to be watertight below the liquid level and to withstand all expected physical forces, to provide for settling of solids, accumulation of sludge and scum, and access for appropriate inspection and cleaning.

- Construct the septic tank from precast reinforced concrete, poured-in-place concrete, concrete block or materials approved by the RMI EPA.

- Provide a substantial and watertight cover to the septic tank.

Absorption and storage

- Conduct effluent to the storage system through watertight PVC pipes and fittings.

- Install distribution pipes for gravity flow absorption systems that are four inches in diameter, perforated, and of material capable of withstanding corrosive action by sewage and sewage generated gases.

- Make one-foot minimum separation between the trench bottom and the maximum groundwater table. Ensure that the scum storage volume consists of 15 per cent or more of the required liquid capacity of the tank and is provided in the space between the liquid surface and the top of inlet and outlet device.

Servicing and cleaning

- Install the septic tank in a location that is accessible for servicing and cleaning.

- Provide properly placed manhole coverings not less than eighteen inches in diameter and hand-hole openings not less than six inches in diameter for cleaning purposes.

Septic systems are only suitable for domestic wastewater, such as from dormitories and classrooms, but not wastewater associated with commercial trade training (for example, from a trade training facility such as hair dressing, mechanical, spray painting etc.).  In the absence of facilities for dealing with trade wastes in RMI it is necessary that if the project finds a need for disposal of such material a suitable waste treatment/neutralization facility shall be designed and installed at the education facility.  An application shall be made to the RMI EPA for approval of any discharge which shall be made in accordance with any permit conditions imposed by RMI EPA.

## Vegetation Impacts

The construction areas at all sites comprise existing school grounds.  As such vegetation impacts will be minimal.  Any works near trees should be managed to avoid damage to trees or their roots. If roots are encountered during any project-related-activities these wherever possible should be left intact and excavation re-routed to avoid the roots and not otherwise cause damage. Replanting may need to be undertaken in some circumstances.  Where practicable, replacement will be on a like-for-like basis.

## Construction works Adjacent to Coastal Areas

The CMI Arrak facility will involve construction of a new facility on CMI leasehold land, ocean-side and across the road from the CMI Arrak campus.

The construction site will be located within 30m of the ocean-side high tide level and will potentially be subject to inundation during future elevated sea levels.  Design should incorporate climate resilient features.  No project construction or other activities will take place seaward of the high tide level.

## Traffic impacts and Impacts on Neighbors

Construction works will be across the road from the existing Arrak CMI campus and contractors will need to provide a Traffic Management Plan if construction activities might interact with traffic.  Also given that the Arrak construction site is not within the existing campus footprint and may therefore be accessible to the general public, attention will need to be given to security and public/community safety.  The construction site is 100-200 meters (330-660 feet) from any neighboring dwellings and therefore will pose no risk in respect of noise and dust generation considering it is a relatively straightforward building construction. Other sites are located away from roads and neighboring residential properties.  Construction works will not pose risks in respect of traffic interference nor will they pose a risk in regard to interference with neighbors on account of site isolation.  Transport of material and equipment will use existing roads and access routes and will not be expected to cause any more than minor community or neighbor risks given that transported quantities will be consistent with minor building works.

As outlined in Section 2.1.3, potential disruptions to learning caused by noise and dust will be addressed by scheduling works during semester breaks which will also reduce traffic congestion and simplify material and equipment transport logistics. Site-specific codes of practice will be developed by contractors using RMI Government and ESMP guidelines.

## EPA Permits

Earthworks activities associated with renovations (Wotje, Jaluit) or new buildings (Gugeegue, Arrak) will require permits from the RMI EPA (see Section 3.2.3).

## Source of Aggregate for Construction

In accordance with World Bank requirements for RMI projects, all aggregates and sands etc. for making concrete will be sourced from overseas.  No locally sourced aggregates or sands etc. will be used. Design can address minimizing reliance on aggregates taking account of costs and practicalities.

# POTENTIAL SOCIAL IMPACTS, RISKS, MITIGATION AND OPPORTUNITIES

## Ensuring Safety in Delivery of After-School Tutoring and Summer School Classes

The provision of after-school and summer-school programs is likely to result in positive benefits for students but could add additional risk for SEAH unless there is sufficient attention to ensuring adequate supervision, teacher/adult accountability, transport logistics, facility selection and management. The MOEST has a policy of child protection which include training for teachers and head teachers and referral process when abuse is reported or suspected. Given that tutoring will be provided by teachers, and most likely in the existing school environment, the risk of additional abuse is limited but should be actively managed. Guidelines will need to be developed detailing supervisory requirements, scheduling stipulations (i.e., avoiding after-dark finishing times and mixing of male/female students of different ages) and safe space assurances (i.e., adequate lighting, visibility etc.).

Risk mitigation strategies to be used when selecting and preparing locations for after-school and summer school programs will include ensuring:

- There is adequate lighting, both within the classroom and in external areas;

- Male and female washrooms are private and secure;

- Provisions are in place to ensure teachers have back-up support in instruction and supervision (i.e., teachers should not be working alone);

- There are windows and doors that allow visibility to classrooms, teacher’s offices and other spaces;

- Availability of age-disaggregated and separated classes, or provision for additional supervision in combined age group settings;

- Programs are held in areas accessible by public transport, linking to private transportation options or utilizing existing school buses/mini vans with licensed and trained drivers, that enable students, tutors and teachers to transit safely and cost effectively, and

- Age-appropriate reporting mechanisms are in place for children and young people who attend after-school and summer sessions.

## Ensuring Computing is Child-Safe

The introduction of computers into education facilities could create a risk of online sexual exploitation and abuse, peer-to-peer bullying, violence amongst students or perpetuated by adults gaining access to children online (through social media, email, interactive sites) unless stringent safeguards are in place.

Given that the provision of IT equipment is supported by the project, it is important to ensure schools have appropriate safeguard systems in place, and teachers and other administrators have the technical skills required to prevent and respond to online SEAH. Mitigation measures could involve training for teachers and students on ‘staying safe online’ and the purchase and installation of child safe software and other safeguards to block inappropriate violent and sexual content.

## Increasing Teacher and Counsellor Awareness and Responsiveness to Social Safeguards

Given the high levels of domestic violence and GBV in the RMI, with over 50 percent of women experiencing intimate partner physical and/or sexual violence in their lifetime (National Gender Mainstreaming Policy), along with the ongoing use of corporal punishment in homes, communities and schools, it is essential that teachers and counsellors are sensitive to these issues and are trained to respond professionally to child protection and domestic violence issues that may arise.

The MOEST has a policy on child protection and has developed resources to train teachers and head teachers on identifying and responding to incidents of reported or suspected abuse, including referral protocols. This policy, and the accompanying procedures, will be reviewed at the outset of the project, in collaboration with the PSS and the Ministry of Culture and Internal Affairs, as the basis for designing relevant training for teachers, counsellors and contracted staff (including contracted trainers, tutors, and mentors) on social safeguards and support methods. This review will also help to inform the design of relevant information, education and communication materials for school personnel, contracted workers, students and school communities.

Teacher, trainer and counsellor training and coaching will be designed to cover:

- Positive behavior management techniques

- Promoting respectful relationships

- Recognizing, reporting and making referring in cases of suspected child abuse, SEAH and GBV

- Strategies to supporting victims of SEAH and GBV to the extent possible

- Increasing understanding of PSS and Project social safeguards.

## Constructing Training Facilities, Dormitories and NTC Facilities in Ebeye and Majuro

### Civil Works

To mitigate safety and other social risks associated with civil works, the project should implement a checklist system within grant monitoring and reporting processes that specify design features to safeguard communities and prevent environmental issues. This includes ensuring that:

- New building and renovation designs include actions to address pollution prevention, resource efficiency (particularly water and aggregates), waste minimization, safe drinking water, fire safety, safety in design, accessibility, climate resilience, co-benefits (such as engineering to allow for solar panels on roofs), cooling / temperature controls;

- Construction activities are mostly restricted to existing campus footprints, and in any case, within existing PSS, NTC or CMI lease areas;

- The PIU advises local communities via SEP prior to commencement of construction so community members are aware of forthcoming works and associated risks;

- MOUs require PSS and NTC to ensure contractors to implement all reasonable precautions to prevent accidents and injuries to staff and workers and protect the health and safety of the community;

- The timing of construction works coincides with school vacation times to minimize disruption and risk to students and staff from workforce activities. If this is not possible, rehabilitation and improvement work should be conducted on weekends and other times when students are not on site;

- Work on water, sanitation and hygiene (WASH) facilities is only completed during periods when the facility is not operating, and that during sanitation upgrades, separate, safe, hygiene and lockable sanitation facilities are provided by boys and girls/men and women;

- Contractors prepare and implement a Contractor’s ESMP, including Worker Health and Safety Management Plans in accordance with Appendix B and, if necessary, a Traffic Management Plan;

- Building design include adequate sanitation facilities for males and females, as well as appropriate WASH and menstruation, management and hygiene provisions;

- Suppliers, contractors, workers and traders undergo reference checks during recruitment procedures;

- All contractor workers sign a Code of Conduct which explicitly prohibits any sexual contact and sexual harassment of children and students;

- All contractors and workers undergo a briefing on the Code of Conduct to ensure they clearly understand the provisions and consequences of breaching including disciplinary measures;

- Students, parents and community leaders are made aware of nature and duration of work including information on reporting incidents or concerns;

- Reporting and grievance mechanisms are in place in the event of harassment, abuse, violence, including clear investigation and accountability procedures;

- Teachers and other project implementers are provided with contact information and referral procedures for victim support;

- The contractor or institute records who is present on the site on a daily basis;

- The visibility of construction areas is maintained. If visibility will be obscured, access to areas surrounding the works should be restricted;

- Contractors develop comprehensive safety plans, which are shared with and agreed by school management. Prior to finalization of site safety plans, students are provided opportunities for input, and

- Safety plans specify that tools are not left unattended; dangerous areas are well marked, fenced off and lit at night; traffic management mechanisms are appropriately included to avoid risks of road accidents; work areas are clearly marked and physical barriers set-up where possible.

### Construction of Dormitories

This subcomponent supports the construction and/or rehabilitation of secondary school dormitories and improvements to the supervision and support of boarding students.

Although it is an existing practice within RMI to send children to live in school dormitories or with extended family in kinship care arrangements, non-parental, alternative care and family separation do pose additional risk of harassment, abuse and/or neglect. Project design recognizes that SEAH can occur in boarding facilities perpetrated by teachers, support staff, community members, or through peer-on-peer violence and bullying, as a result of inadequate supervision and oversight, unsafe facilities, lack of accessible reporting mechanisms and inadequate follow-up.

Of note, only students from outer islands with no other suitable housing options will be eligible to live in the new/refurbished dormitories. Students with relatives on the island where the secondary school is located will be required to stay with them, unless there is a child protection or other significant safeguard concern. Student preferences concerning accommodation arrangements must also be considered from the outset.  Eligibility and selection criteria as well as verification procedures will be defined in the ESSP Project Operations Manual. Consideration will be given to adoption of a lottery process if demand exceeds places available.

Facility Design

As such, boarding facilities will be designed with paramount attention to student safety, incorporating feedback from students, parents, teachers and community stakeholders.  This process could include walk-through tours, and consultations with students, parents, teachers and school management and community leaders.  Design will incorporate consideration of need of both male and female students and include adequate provisions to ensure comfort and safety of both.

Supervision and Support Guidelines

Guidelines to ensure proper supervision and support for students will be drafted and widely reviewed by stakeholders, including school administrators, teachers, academic mentors, parents and student representatives (female and male) to ensure minimal risk of abuse and neglect once dorms are in use.

Mitigation measures include:

- Conducting safety audits of existing dormitories and boarding facilities prior to facility design to identify physical and other factors that contribute to incidents of violence, and perceptions of safety. These audits should include: analysis of the overall layout, lighting, visibility, presence of locks on dormitory internal and external windows and doors, perimeter fencing, availability and appropriateness of sanitation facilities, design of showers, unsupervised areas, divisions in sleeping quarters between age groups and genders, alarm procedures, and safety of transport arrangements for children travelling to and from school;

- Ensuring the results of safety audits are incorporated in design and construction Terms of Reference and / or bid documents;

- Consulting with police, community and church leaders, teachers, parents and students about potential safety issues in schools and dormitories and what systems need to be in place;

- Conducting girl and women-only focus groups to ensure the voices and perspectives of female and male beneficiaries are fully considered in building design, including WASH options. Female focus groups will also enable discussion of gender sensitive WASH topics such as menstruation hygiene management and standards;

- Ensuring appropriate school and boarding facility SEAH reporting mechanisms are in place, aligned with MOEST and GoRMI child protection policies and procedures; and

- Ensuring teachers, trainers, tutors, mentors, supervisors and school/boarding facility management and key employees (including summer school programs personnel) have received appropriate training to understand and recognize abuse and are able to make safe and effective referrals.

### Upgrading NTC’s facilities in Majuro and Ebeye

The proposed civil works to upgrade NTC’s two facilities (one in Majuro, one in Ebeye) will include provisions to address the potential for SEAH.  While the risks of SEAH are similar to those outlined for civil works on TVET institutions and dormitories, there may be differences related to the scale and location of project works and management processes. For instance, ESSP management processes will need to address how civil works can be carried out with least disruption to NTC employees, clients and surrounding businesses and households.

In addition to developing and applying a similar checklist to that proposed for civil works in TVET institutes (under Component 2), upgrading NTC facilities provides an opportunity to ensure that facility design considers safety, gender and accessibility factors. For example, this could include provision of private counselling spaces, physical access for people with disabilities, proper lighting and security, and gender sensitive WASH facilities.

## Providing Stipends to Trainees, Childcare Services; and Subsidies to Interns

The provision of stipends for trainees and interns, and the payment for childcare services will provide increase access for those who may not otherwise be able to afford to attend training, thereby resulting in increased employment opportunities, particularly for those with limited financial means.  Improved access to child care facilities may encourage participation by women and girls who may otherwise have limited options due to family and households responsibilities.  However there is also the potential for exploitation and abuse in relation to placement opportunities and workplace interactions as a result of heightened power differential. To mitigate this and other risks associated with the payment of stipends and childcare support the project must ensure appropriate oversight in the selection of trainees , such as utilizing a panel or two-tier selection process, in conjunction with ensuring there are clear guidelines on relationships between trainees and supervisors.

It will be important to provide clear information about payment terms, conditions and frequency and ensure that implementing agencies adhere to these terms.

## Expanding the Role and Capacity of Counsellors

The Project will include a review and expansion of the role of counsellors within secondary schools, CMI, USP and the NTC to include greater emphasis on continuing education, career pathways, employment preparation and dealing with socio-emotional issues that affect student attendance and achievement. These topics are not adequately addressed in current counsellor training, which provides an opportunity for the project to broaden the range and effectiveness of counselling services for secondary and TVET students.

Within NTC, the range and quality of career counselling and job matching services will be expanded so clients receive broader, more holistic support, including one-on-one job coaching, employment application support and advice, job matching assistance, and referral services to further training and work placement programs in RMI, the Pacific region and to United States of America jurisdictions that host Marshallese migrants.

Increased employment is expected as a result of strengthening the capacity of NTC employment centers, in particular support for intensive job coaching, and referral services for jobseekers lacking requisite foundational skills or work experience.  There is also opportunity to work with survivors of gender-based violence to lift their livelihood opportunities and economic prospects. Enhancing NTC staff capacity for effective engagement with survivors of violence, improving referral protocols to specialized services, while delivering customized career counselling and employment preparation services could provide a successful, multi-faceted approach to meeting the needs of vulnerable young Marshallese.

## Recognizing Prior Learning (RPL)

RPL services will be made available in both Majuro and Ebeye. Stakeholder consultations suggest this activity will be particularly beneficial for those employed in Kwajalein, where the lack of formal qualifications serves to limit wages and career progression. Clear selection criteria will need to be established to assess eligibility for participation in an RPL process funded by the project, with due consideration to gender equity and social inclusion factors.

## Engaging with PIU Team Members

Employment under Component 4 (Project Implementation Support, Planning, Capacity Building, and Monitoring and Evaluation) is likely to result in increased employment opportunities for appropriately qualified people in RMI.  To ensure appropriate workplace behavior, a code of conduct and relevant training will be included in recruitment and onboarding processes.  Staff training on SEAH will be mandatory.

## Understanding Land Access

Virtually all land in RMI is under customary tenure.  The proposed project activities will be undertaken on school properties which are covered under PSS leases; at CMI’s Arrak campus which is covered by CMI’s lease; and on NTC’s Ebeye and Majuro facilities.  All the land is already under Government lease and the activities are consistent with current activities, there will be no need to enter into further lease arrangements with landowners.  The land availability within existing school grounds (Figures 1-6) is considered adequate for all construction activities and therefore project will not involve any involuntary land acquisition or use, and new lease arrangements for construction activities are not anticipated.

## Ensuring Health and Safety

### Community Health and Safety

Potential risks to community health and safety are associated with project construction and mainly comprise minor dust and noise impacts. Construction works are limited to school sites, and isolated from community and public areas. Hence, dust and noise impacts are unlikely to be significant; especially given works will be carried out when students are off-site.

Standard practice for renovations and construction activities on smaller neighbouring islands (other than Majuro or Ebeye) involves use of contracted local workers under supervision by a PSS supervisor.  Civil works will be undertaken in accordance with procedures set out in Section 7.5.1, incorporating contractor contract clauses in Section 9.  Accordingly, there will be no increased risk of GBV or SEAH caused by the importation of off-island worker, and adherence to Codes of Conduct and appropriate supervision will mitigate potential incidents. Construction supervisors will be accommodated in hotel facilities on Wotje and Ebeye (unless the supervisor is from that island); on Jaluit, the supervisor will be accommodated in guest housing at the school, unless the supervisor is from the area.

The same mitigation measures outlined in Section 7.5.1 (Civil Works) will apply to addressing community health and safety concerns.

### Student and Faculty Safety

Design of new facilities and construction upgrades shall incorporate “Safety in Design” in respect of life and fire safety, storage of hazardous materials, extreme weather protection, building cooling, sanitation and provision for disability.  These elements will all contribute to physical aspects of student and faculty safety.

The same mitigation measures outlined in Section 7.5.1 (Civil Works) will apply to addressing potential student and faculty health and safety concerns.

### Construction-related occupational Health and Safety

Civil works required for renovation, extensions and new construction do pose potential occupational health and safety risks which must be effectively and protectively managed from the outset. All construction works will be undertaken by experienced contractors who will be required, by contract, to adopt and enforce OHS plans for project-related activities. Section 8 sets out clauses for inclusion in construction contracts, including OHS requirements.  Annex 2 outlines the requirements for the contractor’s Health and Safety Management Plan.

Similar to other WB-funded projects in the RMI, a Memorandum of Understanding (MOU) will be developed between the Ministry of Finance and the PSS and NTC to ensure successful implementation of the project.  This MOU will establish the terms and conditions under which the MoF will provide financial support to PSS to carry out the identified and agreed renovation and construction works at each school site, and NTC for any construction activities under their control. This MOU will include the requirement that the PSS / NTC shall, at all times, implement all reasonable precautions to prevent potential accidents and injuries to staff and workers, and to protect the health and safety of the community.  Annex 2 sets out a Health and Safety Management Plan Guideline which could inform the Contractor’s consideration of “all reasonable precautions”.

# CIVIL WORKS CONTRACTOR – ENVIRONMENTAL, SOCIAL, HEALTH AND SAFETY CLAUSES

It is expected that PSS and NTC will engage a contractor to undertake construction and renovation works, with MWIU PMU oversight, as is the practice for other RMI WB-funded education sector projects.

Instructions to MWIU PMU or other agency preparing the contractor’s bid documents:

The following environmental, social, health and safety clauses shall be incorporated in bid documents for contracted works.  Site-specific mitigation to be inserted in the bid documents, along with the specific mitigation measures prescribed in this ESMP.

The CIU safeguards advisors will be responsible for the oversight of the environmental, social, health and safety activities of the contractor, and will review draft bid documents, review the Contractor’s Environmental and Social Management Plan (C-ESMP) and will conduct periodic on-site visits to monitor and supervise progress.  The CIU safeguards advisors will train the MWIU PMU staff on basic environmental, social, health and safety activities and mitigation measures so that they can provide contractor oversight in-between CIU safeguards advisor site visits.

## General – Preparation of Contractor’s Environmental and Social Management Plan

The Contractor must prepare an Environmental and Social Management Plan, to be cleared by the client prior to works starting, which includes the following:

- Health and Safety Management Plan (refer to Annex 2 of the Project ESMP for details);

- Staff responsible for environmental management, consultation and community liaison, health and safety management, complaints management and reporting to the client;

- Risk register documenting the site-specific and project specific risks;

- Mitigation measures for all medium, high or very high risks, including detailed procedures, diagrams and other explanations about how they will be implemented and monitored;

- For any projects where asbestos or other hazards have been identified by the client, the ESMP should include the relevant identification, management, storage and disposal practices;

- Waste management plan, which should include the types and volumes of waste expected, how waste will be reused or recycled within the local / island community, waste storage, transportation to Majuro or other international port, and export to a suitable disposal facility overseas, including procedures for export permits and other relevant approvals;

- Traffic management plan where traffic-related risks are identified as medium, high or very high.  This should include what controls are required for truck drivers (training, qualifications, speed, times of day for transportation of equipment), what controls are required to warn motorists and pedestrians about transport-related risks (heavy loads, wide loads, slow vehicles);

- Training plan and training records relating to environmental controls, consultation and social impact management, health and safety.

- Other matters as listed below.

## Potential Asbestos Containing Material or Lead Paint

If, during the course of construction, materials, structures or other infrastructure is discovered that has the potential to contain asbestos the Construction Contractor should immediately cease works and contact the CIU Safeguards Adviser for advice.  An Asbestos Management Plan will be prepared prior to the commencement of construction works.

The Construction Contractor shall test painted surfaces for lead prior to demolition or renovation.  If paint tests positive for lead, procedures will be developed to contain the materials and avoid environmental release. Disposal requirements will be outlined in the Waste Management Plan.

## Community and Worker Health and Safety

Site-specific mitigation to be inserted in the bid documents.

- The Contractor shall at all times implement all reasonable precautions to prevent and reduce accidents and injuries to staff and workers and protect the health and safety of the community.

- The Contractor shall prepare and implement a Health and Safety Management Plan commensurate with the identified health and safety hazards at the construction site and it shall include activities related to construction (such as the transportation of materials r).

- The Contractor shall at all times provide and maintain construction plant, equipment and systems of work that are safe and without risks to health. This shall include maintaining equipment, engines, and related electrical installations in good working order; maintaining a clean and tidy workspace; providing guards and rails, signals and lighting; providing work site rules, safe working procedures and allocating appropriate places to carry out the work.

- The Contractor shall provide, at his/her own expense, the protective clothing and safety equipment to all staff and labor engaged on the Works to the satisfaction of the Employer’s representative. Such clothing and equipment shall include, as a minimum:

  - high visibility vests for workers directing traffic;

  - protective boots and gloves for the workforce undertaking excavation works;

If the Contractor fails to provide such clothing and equipment, the Employer shall be entitled to provide the same and recover the costs from the Contractor.

- All the Contractor's personnel shall, before commencing work, have an induction course on environmental management and safety and health at the site. The information and training shall be on the site and have duration of at least two hours.

- The Contractor shall prepare and implement a Traffic Management Plan to ensure that any traffic and/or pedestrian hazards caused by the works are adequately managed.

## Waste Management

Site-specific mitigation to be inserted in the bid documents.

- The Contractor shall prepare a Waste Management Plan as per the General Clause above.

- The Contractor shall, at all times, keep construction areas, including storage areas used, free from accumulations of waste materials or rubbish.

- Contractor ensures all construction waste is recycled or re-used as far as practicable at all construction locations.

- All residual waste shall be stored and handled on site in accordance with the requirements of the Solid Waste Regulations 1989 and the World Bank Group EHS Guidelines to avoid littering and pollution to ground, coastlines or water.

- All waste that is not able to be reused or recycled locally shall be contained and exported to a suitable recycling or waste disposal facility, in compliance with international regulations.  The details of waste export shall be contained within the Waste Management Plan, for clearance by the client prior to implementation.  All documentation for export, including permits, receipts, tracking documentation will be shared with the client for verification.

- All wastewater and sewage from construction facilities shall be managed in accordance with Project ESMP, national and local government requirements and World Bank Group EHS Guidelines, and the Contractor shall, as necessary, obtain a permit or other appropriate documentation approving the storage, treatment and disposal methods being used.  The Contractor shall provide details in the C-ESMP.

## Prevention of Water and Air Pollution

Site-specific mitigation to be inserted in the bid documents.

- The Contractor’s construction activities shall be performed by methods that will prevent entry, or accidental spillage, of solid matter, contaminants, debris, and other pollutants and wastes into marine waters and underground water sources. Such pollutants and wastes include, but are not restricted to, refuse, garbage, cement, sanitary waste, and oil and other petroleum products.

- Excavated materials or other construction materials shall not be stockpiled or deposited near or on waterbody perimeters or in a position where storm water runoff can entrain sediment and cause turbidity in waterbodies.

- Wastewaters from concrete preparation, or other construction operations, shall not be permitted to enter waterbodies without the use of control methods such as sediment filters.

- During the conduct of construction activities and operation of equipment, the Contractor shall utilize such practicable methods and devices as are reasonably available to control, prevent, and otherwise minimize atmospheric emissions or discharges of air contaminants.

- Equipment that shows excessive emissions of exhaust gases due to poor engine adjustments, or other inefficient operating conditions, shall not be operated until corrective repairs or adjustments are made.

- During the performance of the construction works the Contractor shall carry out proper and efficient measures wherever and as often as necessary to reduce the dust nuisance, and to prevent dust which has originated from its operations from damaging dwellings or causing a nuisance to persons.

## Preservation of Vegetation

Site-specific mitigation to be inserted in the bid documents.

- All trees and other vegetation shall be preserved and shall be protected from damage by the Contractor’s construction operations and equipment.;

- Movement of labor and equipment for access to the work shall be performed in a manner to prevent damage to vegetation or property.

## Construction Facilities

- The Contractor’s workshops, office, and yard area shall be located and arranged in a manner to preserve trees and vegetation and minimize impacts to local communities, as per agreed Organizational Plan.

- On completion of works, all temporary buildings, including any concrete footings and slabs, and all construction materials and debris shall be removed from the site.

## Sourcing of Aggregates for Construction

- All aggregates used for project works shall be sourced from outside of RMI.

## Worker Accommodation

- All workers shall be provided with safe and healthy accommodation, with potable drinking supply, running water, septic tank or reticulated wastewater collection and treatment, separate sleeping quarters (with separation of washrooms, bedrooms and toilets for men and women), and access to recreation areas / facilities.  No new workers camps or worker accommodation facilities will be constructed (permanently or temporarily) for the workforce.

## Worker Code of Conduct

- All workers shall be required to sign and adhere to a code of conduct relating to worker behavior to avoid harm to community members.  Training will be provided to outline appropriate behaviour and sanctions for non conformance.

## Cultural Heritage Chance Find Procedures

- In accordance with the RMI Historic Preservation Act 1991, when a person working on the project discovers a cultural heritage site or item, the following procedures should be followed:

  - Stop the activities in the area of the chance find.

  - Delineate the discovered site or area (e.g. fencing).

  - Secure the site to prevent any further disturbance, damage or loss. In cases of human remains, arrange for a guard to watch the site until the police, local government and / or National Cultural Commission representative or person with delegated authority take over.

  - Prohibit the collection of any object by any person.

  - Notify the local government and RMI Historic Preservation Office within 24 hours (and police if it is human remains).

  - Any objects that are found must be handed over to the Historic Preservation Office.

  - Project works can resume only after instruction is provided from the Historic Preservation Office.

# STAKEHOLDER ENGAGEMENT

The SEP has been developed as a stand-alone document, and attached in Annex 4.  The Grievance Mechanism set out below in this ESMP is adopted in the SEP.  A summary of the SEP is provided in this section.

The main objective of the SEP is to define a program for stakeholder engagement, including public information disclosure and consultation, throughout the entire project cycle. It also outlines a communication strategy with the project stakeholders and offers mechanisms for stakeholders to raise concerns, provide feedback, or make complaints about project.

Stakeholder engagement is critical in the development of the project to understand the opportunities and risks relating to the proposed components.

Stakeholder engagement has been undertaken as part of the preparation of this ESMP, and will continue throughout the life of the project, particularly in the early stages when project details are finalized.

As set out in the SEP, broader consultations relating to the project development and implementation will be undertaken in culturally appropriate formats; and where appropriate, consultations may be gender focussed to identify specific education issues relating to gender and SEAH.

## Key Stakeholders

The key stakeholders of the ESSP Project include:

- Marshallese youth and their families

- Education and training sector

- Private sector employers in RMI

- Schools where project works will take place, and neighbouring communities

- School administrators, teachers, and counsellors at each facility

- Students at each facility

## Engagement during Development of Safeguards Instruments

Initial consultations were held with staff from NTC and PSS between June and August 2020 to seek feedback on project design and discuss safeguard elements.  Principals from high schools on Jaluit, Wotje and Gugeegue were also consulted at a meeting in Majuro in July.

Other meetings were held as follows to discuss project safeguards issues: College of the Marshall Islands (7th August 2020); Ace Hardware (10th August 2020); Majuro Water and Sewer Company (19th August 2020); National Telecommunications Authority (19th August 2020); Youth2Youth (19th August 2020)

Consultations could not be held with communities on Jaluit, Wotje or Ebeye, and stakeholder engagement with these groups is proposed under the SEP, including how the results of consultation will be incorporated in implementation.

## Engagement with community stakeholders during Construction Works

Consultation with stakeholders potentially affected by construction activities will take place in two phases:

- Direct engagement with residents and community’s resident or working in areas close to proposed building activities. This consultation will be required to inform the residents and communities of any potential disruption associated with the works, and should be undertaken face-to-face.  During these meetings, the scope of works will be described in detail, including the timing, likely impacts, and details on the grievance redress mechanism.  Consultation should also be undertaken once the building programme has been determined and then again two weeks prior to construction commencing; and

- Public notification of civil works. Whilst the construction works are unlikely to cause broader disruption and inconvenience, notices should be published to advise people about the upcoming works including timing, duration and grievance redress procedures.

Consultation should be undertaken by the contractor’s supervisor pursuant to the SEP program, with oversight by CIU safeguards personnel.

## Engagement of technical experts during Project preparation and inception

It may be necessary to recruit consultants/contractors to assist project implementing agencies with some elements of implementation such as review and development of TVET curriculum, design of renovated facilities, training for counsellors etc.  This work will be guided by ongoing consultation with key stakeholders including contractor’s supervisor pursuant to the SEP program, with oversight by CIU safeguards personnel.

# GRIEVANCE MECHANISM

The SEP in Annex 4 sets out the project GM whereby project stakeholders, beneficiaries and members of the public can make contact with personnel involved with the project to raise issues, concerns, complaints or queries and have those matters addressed in an expeditious manner.

The best methods to ensure that the GM is widely accessible, easy to understand (i.e. available in Marshallese and English) and locally relevant to stakeholders in different locations will be identified during project inception, before commencement of any activities.  GM development and distribution with include involvement of staff from all implementing agencies, discussion with media outlets (newspaper and radio), the Ministry of Culture and Internal Affairs and the Marshall Islands Major’s Association.  The project will also ensure regular review of the GM to ensure concerns are being identify and addressed proactively and effectively.

The GM accommodates any person who may wish to find information about the project or who may seek to express a dissatisfaction, concern, or complaint about the project because they believe they have been or will be negatively impacted by project activities. Concerns may be raised about facilities or services provided, or about actions or lack of actions taken, and concerns can be raised by individuals or groups.

# MONITORING AND REPORTING

The CIU environmental and social team is responsible for monitoring and reporting on implementation and outcomes of the ESMP, SEP (including GM) and LMP, and reporting to DIDA.  Specific monitoring tasks include:

- LMP: Checking that LMP has been complied with on engagement of direct and contracted workers.  Each process will be checked prior to contract signing and CIU environmental and social team will provide feedback to ensure compliance.

- LMP: Checking that the LMP GM has been explained to workers and that grievances are being managed and closed out as per the LMP and ESS2.  Within two months of workers being engaged and the GM progress checked at least 6 monthly or within one month of a grievance being lodged.

- Facility Design: The CIU environmental and social team will monitor the design outputs to check against the ESMP, EHG Guidelines and ESS to ensure there is compliance prior to bid documents being prepared.  CIU feedback will be incorporated into final design.

- Works: The CIU environmental specialist will conduct at least monthly visits to work sites to monitor the environmental and social performance of Contractors.  The first visit will be prior to works commencing.  Once the CESMP is approved, the CIU environmental specialist will prepare a checklist for site visits to observe compliance with the CESMP.  All monitoring will be observational.

- Works: The MWIU will conduct environmental and social audits during their regular work site visits to monitor the environmental and social performance or Contractors. The CIU environmental specialist will prepare a checklist for MWIU site visits. Any non-conformances will be reported to the CIU environmental specialist and an action plan will be prepared and implemented to resolve the non-conformance.  All monitoring will be observational.

- GM: The CIU social specialist will monitor GM implementation on a 2 monthly basis, recording – number of grievances, complaints and queries lodged, number outstanding, number closed.

- Incident monitoring: Any complaints or incidents, such as noise, will be monitored on a case by case basis.

The CIU environmental and social team will provide 6 monthly reports to DIDA.  Reports will include a progress report, monitoring outcomes, incidents, and summary of key risks requiring management.

In the case of a environmental or social incident, this will be promptly reported by the Project to the Bank.  This will include any incident or accident related to the Project which has, or is likely to have, a significant adverse effect on the environment, the affected communities, the public or workers.  Minor incidents will be reflected in the six-monthly reports but serious incidents will be notified immediately (within 24 hrs) with follow up as necessary.

# CAPACITY DEVELOPMENT

The CIU environmental and social team will work with the PIU to apply the ESMP and other instruments as required throughout the project.  The team will contribute to the development of annual work plans, and ensure activities such as consultation, environmental and social site visits and review of bid documents are included.

This team is responsible for training the PIU, CIU, Project Steering Committee, NTC, PSS and MWIU staff involved in the project on their environmental and social roles and responsibilities.  Such as:

- Training the MWIU on the requirements for preparing EHS and social clauses in the bid documents and supervising the C-ESMP in-between CIU team visits.

- Training all those involved in the GM including SEA/SH

- Consultation and engagement training, awareness raising and support.

- ESMP, RMI legal obligations and WB Group EHS Guidelines requirements for facility design, construction and operation.

- LMP requirements for engagement of direct and contracted workers.

Specialist resources will be engaged to address SEA/SH risks, deliver training on the code of conduct, and support SEA/SH related grievances if applicable.  A framework budget will be agreed during implementation which will be based on final construction design and geographic support needs.

# BUDGET

The following is an indicative budget for implementing the ESMP. These items are over and above those considered to be covered by normal operations and normal duties of the CIU environmental and social team, which are covered by CIU budget.  Contractors environmental and social management will be incorporated into the Contractor’s costs.

| Budget Item | Detail | Cost Estimate (USD) |
| --- | --- | --- |
| Stakeholder consultations | Catering, venue hire, media, materials, travel and accommodation, translation and interpretation services, etc. | $30,000 |
| Capacity development training, awareness raising including SEA/SH. | Venue, stationery, refreshments, training materials and delivery. | $10,000 |
| Monitoring and reporting | Travel and accommodation costs in Ebeye, Wotje, Jaluit; report production costs (non-staff costs); | $15,000 |
| GM related costs | Personnel, communication, transportation, office support costs include SEA/SH | $10,000 |
| Total |  | $65,000 |

# ANNEXES

Annex 1: 	Abbreviations and Acronyms

Annex 2: 	Health and Safety Management Plan Guidelines

Annex 3: 	Risk Assessment Methodology

Annex 4: 	Stakeholder Engagement Plan (including Grievance Mechanism)

# Annex 1: Abbreviations and Acronyms

| CEDAW | Convention on the Elimination of all forms of Discrimination Against Women |
| --- | --- |
| CIU | Centralized Implementation Unit of DIDA |
| CMI | College of the Marshall Islands |
| CRC | Convention on the Rights of the Child |
| CRPD | Convention on the Rights of Persons with Disabilities |
| DIDA | Division of International Development Assistance |
| EHS | Environmental, Health and Safety |
| EIA | Environmental Impact Assessment |
| EMP | Environmental Management Plan |
| EPA | Environmental Protection Authority |
| ESMP | Environmental and Social Management Plan |
| ESRS | Environmental and Social Review Summary |
| ESS | World Bank Environmental and Social Standards |
| ESSP | Education and Skills Strengthening Project |
| GBV | Gender Based Violence |
| GM | Grievance Mechanism |
| GoRMI | Government of the Republic of the Marshall Islands |
| JSA | Job Safety Analyses |
| LMP | Labor Management Procedure |
| MOEST | Ministry of Education, Sport and Training |
| MOF | Ministry of Finance |
| MWIU | Ministry of Works, Infrastructure and Utilities |
| NEPA | National Environmental Protection Act |
| NTC | National Training Council |
| OHS | Occupational Health and Safety |
| PEA | Preliminary Environmental Assessment |
| PIU | Project Implementation Unit (for ESSP) |
| PMU | Project Management Unit (of the MWIU) |
| PPE | Personal protective equipment |
| PSC | Public Service Commission |
| PSS | Public School System |
| RMI | Republic of the Marshall Islands |
| RPL | Recognised Prior Learning |
| SEAH | Sexual Exploitation and Abuse and Sexual Harassment |
| SEP | Stakeholder Engagement Plan |
| TVET | Technical and vocational education and training |
| USP | University of the South Pacific |
| WASH | Water, sanitation and hygiene |
| WB | World Bank |

# Annex 2: Health and Safety Management Plan Guidelines

##### OBJECTIVE

The objective of these Guidelines is to provide guidance on the:

- key principles involved in ensuring the health and safety of workers and the community is protected;

- preparation of Health and Safety Management Pan and associated Job Safety Analyses (JSA); and

- implementation of Health and Safety Management Plan and JSA during project implementation.

The key reference document for this Guideline is the World Bank Group’s Environmental, Health, and Safety (EHS) Guidelines (April 2007) together with the relevant Industry Sector EHS Guidelines available at www.ifc.org/ehsguidelines.

##### PRINCIPLES

Employers must take all reasonable practicable steps to protect the health and safety of workers and the community and provide and maintain a safe and healthy working environment. The following key principles are relevant to maintaining worker health and safety:

###### Identification and assessment of hazards

Each employer must establish and maintain effective methods for:

- Systematically identifying existing and potential hazards to employees and the community;

- Systematically identifying, at the earliest practicable time, new hazards to employees and the community;

- Regularly assessing the extent to which a hazard poses a risk to employees and the community.

###### Management of identified hazards

Each employer must apply prevention and control measures to control hazards which are identified and assessed as posing a threat to the safety, health or welfare of employees and the community, and where practicable, the hazard shall he eliminated. The following preventive and protective measures must be implemented order of priority:

- Eliminating the hazard by removing the activity from the work process;

- Controlling the hazard at its source through engineering controls;

- Minimizing the hazard through design of safe work systems;

- Providing appropriate personal protective equipment (PPE).

The application of prevention and control measures to occupational hazards should be based on comprehensive job safety analyses (JSA). The results of these analyses should be prioritized as part of an action plan based on the likelihood and severity of the consequence of exposure to the identified hazards.

###### Training and supervision

Each employer must take all reasonable practicable steps to provide to employees (in appropriate languages) the necessary information, instruction; training and supervision to protect each employee's health and to manage emergencies that might reasonably be expected to arise in the course of work. Training and supervision extends to the correct use of PPE and providing employees with appropriate incentives to use PPE.

###### General duty of employees

Each employee shall:

    - take all reasonable care to protect their own and fellow workers health and safety at the workplace and, as appropriate, other persons in the vicinity of the workplace;

    - use PPE and other safety equipment supplied as required; and

    - not use PPE or other safety equipment for any purpose not directly related to the work for which it is provided.

###### Protective clothing and equipment

Each employer shall:

- provide, maintain, and make accessible to employees the PPE necessary to avoid injury and damage to their health;

- take all reasonably practicable steps to ensure that employees use that PPE in the circumstances for which it is provided; and

- make provision at the workplace for PPE to be cleaned and securely stored without risk of damage when not required.

The application of prevention and control measures to occupational hazards should be based on comprehensive job safety analyses (JSA). The results of these analyses should be prioritized as part of an action plan based on the likelihood and severity of the consequence of exposure to the identified hazards.

##### Design

Effective management of health and safety issues requires the inclusion of health and safety considerations during design processes in an organized, hierarchical manner that includes the following steps:

- identifying project health and safety hazards and associated risks as early as possible in the project cycle including the incorporation of health and safety considerations into the worksite selection process and construction methodologies;

- involving health and safety professionals who have the experience, competence, and training necessary to assess and manage health and safety risks;

- understanding the likelihood and magnitude of health and safety risks, based on:

  - the nature of the project activities, such as whether the project will involve hazardous materials or processes;

  - the potential consequences to workers if hazards are not adequately managed;

  - designing and implementing risk management strategies with the objective of reducing the risk to human health;

  - prioritising strategies that eliminate the cause of the hazard at its source by selecting less hazardous materials or processes that avoid the need for health and safety controls;

  - when impact avoidance is not feasible, incorporating engineering and management controls to reduce or minimize the possibility and magnitude of undesired consequences;

  - preparing workers and nearby communities to respond to accidents, including providing technical resources to effectively and safely control such events; and

  - Improving health and safety performance through a combination of ongoing monitoring of facility performance and effective accountability.

##### Job Safety Analysis

Job safety analysis (JSA) is a process involving the identification of potential health and safety hazards from a particular work activity and designing risk control measures to eliminate the hazards or reduce the risk to an acceptable level. JSAs must be undertaken for discrete project activities such that the risks can be readily identified and appropriate risk management measures designed.

This Guideline includes a template for a JSA that must be completed and included as an attachment to the Health and Safety Sub-plan.

##### Implementation

###### Documentation

A Health and Safety Management Plan must be prepared and approved prior to any works commencing on site. The Health and Safety Management Plan must demonstrate the Contractor understands of how to manage safety and a commitment to providing a workplace that enables all work activities to be carried out safely. The Health and Safety Management Plan must detail reasonably practicable measures to eliminate or minimise risks to the health, safety and welfare of workers, contractors, visitors, and anyone else who may be affected by the operations. The Health and Safety Management Plan must be prepared in accordance with the World Bank Group EH&S Guidelines.

###### Training and Awareness

Provisions should be made to provide health and safety orientation training to all new employees to ensure they are apprised of the basic site rules of work at / on the site and of personal protection and preventing injury to fellow employees. Training should consist of basic hazard awareness, site-specific hazards, safe work practices, and emergency procedures for fire, evacuation, and natural disaster, as appropriate.

Visitors to worksites must be provided with a site induction prior to entering and must be escorted at all times while on site. This induction must include details of site hazards, provision of necessary PPE and emergency procedures. Visitors are not permitted to access to areas where hazardous conditions or substances may be present, unless appropriately inducted.

###### Personal Protective Equipment (PPE)

Personal Protective Equipment (PPE) provides additional protection to workers exposed to workplace hazards in conjunction with other facility controls and safety systems.

PPE is considered to be a last resort that is above and beyond the other facility controls and provides the worker with an extra level of personal protection. The table below presents general examples of occupational hazards and types of PPE available for different purposes. Recommended measures for use of PPE in the workplace include: ·

•	Active use of PPE if alternative technologies, work plans or procedures cannot eliminate, or sufficiently reduce, a hazard or exposure;

•	Identification and provision of appropriate PPE that offers adequate protection to the worker, co-workers, and occasional visitors, without incurring unnecessary inconvenience to the individual;

•	Proper maintenance of PPE, including cleaning when dirty and replacement when damaged or worn out. Proper use of PPE should be part of the recurrent training programs for Employees

•	Selection of PPE should be based on the hazard and risk ranking described earlier in this section, and selected according to criteria on performance and testing established.

| Objective | Workplace Hazards | Suggested PPE |
| --- | --- | --- |
| Eye and face protection | Flying particles, molten metal, liquid chemicals, gases or vapors, light radiation. | Safety Glasses with side-shields, protective shades, etc. |
| Head protection | Falling objects, inadequate height clearance, and overhead power cords. | Plastic Helmets with top and side impact protection. |
| Hearing protection | Noise, ultra-sound. | Hearing protectors (ear plugs or ear muffs). |
| Foot protection | Falling or rolling objects, pointed objects. Corrosive or hot liquids. | Safety shoes and boots for protection against moving & falling objects, liquids and chemicals. |
| Hand protection | Hazardous materials, cuts or lacerations, vibrations, extreme temperatures. | Gloves made of rubber or synthetic materials (Neoprene), leather, steel, insulating materials, etc. |
| Respiratory protection | Dust, fogs, fumes, mists, gases, smokes, vapors. | Facemasks with appropriate filters for dust removal and air purification (chemicals, mists, vapors and gases). Single or multi- gas personal monitors, if available. |
|  | Oxygen deficiency | Portable or supplied air (fixed lines). On-site rescue equipment. |
| Body/leg protection | Extreme temperatures, hazardous materials, biological agents, cutting and laceration. | Insulating clothing, body suits aprons etc. of appropriate materials. |

##### Monitoring

Occupational health and safety monitoring programs should be part of the Health and Safety Management Plan and verify the effectiveness of prevention and control strategies. The selected indicators should be representative of the most significant occupational, health, and safety hazards, and the implementation of prevention and control strategies. The occupational health and safety monitoring program should include:

Safety inspection, testing and calibration: This should include regular inspection and testing of all safety features and hazard control measures focusing on engineering and personal protective features, work procedures, places of work, installations, equipment, and tools used. The inspection should verify that issued PPE continues to provide adequate protection and is being worn as required.

Surveillance of the working environment: Employers should document compliance using an appropriate combination of portable and stationary sampling and monitoring instruments. Monitoring and analyses should be conducted according to internationally recognized methods and standards.

Surveillance of workers health: When extraordinary protective measures are required (for example, against hazardous compounds), workers should be provided appropriate and relevant health surveillance prior to first exposure, and at regular intervals thereafter.

Training: Training activities for employees and visitors should be adequately monitored and documented (curriculum, duration, and participants). Emergency exercises, including fire drills, should be documented adequately.

Accidents and Diseases monitoring: The employer should establish procedures and systems for reporting and recording:

- Occupational accidents and diseases

- Dangerous occurrences and incidents

These systems should enable workers to report immediately to their immediate supervisor any situation they believe presents a serious danger to life or health.

All reported occupational accidents, occupational diseases, dangerous occurrences, and incidents together with near misses should be investigated with the assistance of a person knowledgeable and competent in occupational safety. The investigation should:

- Establish what happened

- Determine the cause of what happened

- Identify measures necessary to prevent a recurrence

Job Safety Analysis (JSA)

Add Organisation Name:

Ref:	Version:

| Business details |  |  |  |  |
| --- | --- | --- | --- | --- |
| Business name: |  | Contact person: |  |  |
| Address: |  | Contact position: |  |  |
| Contact phone number |  | Contact email address: |  |  |
| Job Safety Analysis details |  |  |  |  |
| Work activity: |  |  | Location: |  |
| Who are involved in the activity: |  |  | This job analysis has been authorised by: Name: ................................................................................................................ Position:............................................................................................................. Signature: .......................................................................................................... Date: .................................................................................................................. |  |
| Plant and equipment used: |  |  |  |  |
| Maintenance checks required: |  |  |  |  |
| Tools used: |  |  |  |  |
| Materials used: |  |  |  |  |
| Personal protective equipment: |  |  |  |  |
| Certificates, permits and/approvals required |  |  |  |  |
| Relevant EHG Guideline, codes, standard MSDSs etc applicable to this activity |  |  |  |  |

Risk Assessment

**Use the risk rating table to assess the level of risk for each job step.

|  |  | Likelihood |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | 1 | 2 | 3 | 4 | 5 |
| Consequence |  | Rare The event may occur in exceptional circumstances | Unlikely The event could occur sometimes | Moderate The event should occur sometimes | Likely The event will probably occur in most circumstances | Almost Certain The event is expected to occur in most circumstances |
| 1 | Insignificant No injuries or health issues | LOW | LOW | LOW | LOW | MODERATE |
| 2 | Minor First aid treatment | LOW | LOW | MODERATE | MODERATE | HIGH |
| 3 | Moderate Medical treatment, potential LTI | LOW | MODERATE | HIGH | HIGH | CRITICAL |
| 4 | Major Permanent disability or disease | LOW | MODERATE | HIGH | CRITICAL | CATASTROPHIC |
| 5 | Extreme Death | MODERATE | HIGH | CRITICAL | CATASTROPHIC | CATASTROPHIC |

Risk rating

Low risk:	Acceptable risk and no further action required as long as risk has been minimized as possible. Risk needs to be reviewed periodically.

Moderate risk:	Tolerable with further action required to minimize risk. Risk needs to be reviewed periodically. High risk:	Tolerable with further action required to minimize risk. Risk needs to be reviewed continuously. Critical risk:	Unacceptable risk and further action required immediately to minimize risk.

Catastrophic:	Unacceptable risk and urgent action required to minimize risk.

Risk controls

The hierarchy of control can be used as an effective tool to deal with health and safety issues at work. Use the type of control suggested as measures to deal with the hazard.  Aim to use control measures from as high on the hierarchy of control list as possible. If that is not possible the next option down the list or a combination of the measures should be implemented. The least effective control measure is the use of personal protective equipment (PPE) and it should be used as a last resort or a support to other control measures. Information and training should be integrated with all levels of control to explain how controls work.

- Eliminate – if it is possible, the hazard should be removed completely.  For example, get rid of dangerous machines.

- Substitute – replace something that produces the hazard with something that does not produce a hazard. For example, replacing solvent based paint with water based paint. Risk assessment on the substitution must be conducted to ensure that it will not pose another hazard.

- Engineering control – isolate a person from the hazard by creating physical barrier or making changes to process, equipment or plant to reduce the hazard.  For example, install ventilation  systems.

- Administrative control – change the way a person works by establishing policies and procedures to minimize the risks.  For example, job scheduling to limit exposure and posting hazard signs.

- Use personal protective equipment (PPE) – protect a person from the hazard by wearing PPE. For example, wearing gloves, safety glasses, hard hats and high-visibility clothing. PPE must be correctly fitted, used and maintained to provide protection.

JSA – Action steps

| Step No | Job step details | Potential hazards | Risk rating** | How to control risks*** | Name of persons responsible for work |
| --- | --- | --- | --- | --- | --- |

Review number:	Version:	Review number:	Version:

| This job safety analysis has been developed through consultation with our employees and has been read, understood and signed by all employees undertaking the works: |  |  |
| --- | --- | --- |
| Print Names: | Signatures: | Dates: |

| Review No | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Initial: |  |  |  |  |  |  |  |  |
| Date: |  |  |  |  |  |  |  |  |

# Annex 3: Risk Assessment Methodology

STEP 1

Assign a rating and score for each of the three criteria (A-C) listed in the table below, and then add the scores to determine the consequence rating for an impact.

| RATING | DEFINITION OF RATING | SCORE |
| --- | --- | --- |
| A. Extent – the area over which the impact will be experienced |  |  |
| Local | Confined to the project site or study area | 1 |
| Wider catchment or province | Extends beyond the project site to the wider, surrounding area. | 2 |
| Island or national | Extends to the whole island or nation. | 3 |
| Regional or global | Extends to the Pacific region and potentially beyond. | 4 |
| B. Intensity – the magnitude of the impact i.e. whether the impact will result in minor, moderate or major environmental, economic and social (including human health) changes |  |  |
| Low | Minor or negligible changes, disturbances, damages, injuries or health effects. Likely to generate minimal interest or concern amongst the local community/stakeholders. Examples: dust and exhaust gases from construction machinery; temporary or single exceedance of a pollution limit or threshold; first aid cases; minor discomfort or irritation from construction noise; increased traffic on local roads to transport construction materials to a project site. | 1 |
| Medium | Moderate changes, disturbances, damages, injuries or health effects. Likely to generate more prolonged interest or concern amongst local community/stakeholders. Examples: generation of hazardous waste; large fish kill incident; frequent exceedance of a pollution limit or threshold; clearance of village food gardens; influx of workers from overseas for project construction; moderate disruption of daily life/work activities within a village; intermittent production of foul odour near a village; infrastructure damage from flooding or strong winds. | 2 |
| High | Major or severe changes, disturbances, damages, injuries or health effects. Likely to generate widespread and intense interest or controversy amongst local, national and regional communities/ stakeholders. Examples: clearance of endangered species habitat; drawdown of limited groundwater supplies; large increase in suspended sediment levels from dredging; destruction of cultural artefacts; forced relocation of village settlements; permanent disabilities or fatalities; loss of coastal buildings and infrastructure due to extreme weather events. | 3 |
| C. Duration – the timeframe over which the impact will be experienced and its reversibility |  |  |
| Short-term | Up to 2 years – impact is reversible or limited to when particular development activities or environmental events are taking place. Remediation or recovery is possible. | 1 |
| Medium-term | 2 to 15 years – impact is reversible or limited to when particular development activities or environmental events are taking place. Remediation or recovery is possible. | 2 |

| Long-term | More than 15 years – impact is permanent or gradually reversible with sustained remediation and recovery efforts. | 3 |
| --- | --- | --- |

The combined score of the three criteria (extent, intensity, duration) corresponds to a consequence rating, as follows:

| Combined score (A+B+C) | 3 – 4 | 5 – 6 | 7 – 8 | 9 – 10 |
| --- | --- | --- | --- | --- |
| Consequence rating | Minor | Moderate | Major | Massive |

STEP 2

Assess the probability of the impact occurring according to the following definitions:

| Probability – the likelihood of the impact occurring |  |
| --- | --- |
| Improbable | Unlikely to occur during project lifetime. < 20% chance of occurring |
| Possible | May occur during project lifetime. 20%–60% chance of occurring |
| Probable | Likely to occur during project lifetime. > 60%–90% chance of occurring |
| Highly probable | Highly likely to occur, or likely to occur more than once during project lifetime. > 90% chance of occurring |

STEP 3

Determine the overall significance of the impact as a combination of the consequence and probability ratings, as set out in the matrix below:

STEP 4

State the level of confidence in the assessment of the impact as high, medium, or low. The level of confidence will depend on the extent and type of information available, whether it is qualitative or quantitative, and whether it is based on direct measurements, extrapolated data, estimations or expert opinion.

STEP 5

5(a) – identify and describe practical mitigation measures that can be effectively implemented to reduce the impact.

5(b) – assume mitigation measures have been implemented and reassess the impact, by following steps 1 to 4 again. The point of the second assessment is to examine how impact extent, intensity, duration and/or probability are likely to change, after mitigation measures have been put in place.

STEP 6

Summarize all the impact assessment ratings in a single table that can be included in the executive summary or concluding section of report.

This risk assessment assesses the likelihood and consequence of the potential impacts of the ESSP. The risk assessments for the various impacts identified in Section 6 of the ESMP are summarized below based on this methodology. Table 3-1 summarizes the expected significance of impacts “without mitigation”, details the proposed mitigation measures to mitigate the impacts and summarizes the residual impact significance following implementation of mitigation measures.

The assessed significance of the impact can be seen both prior to and after the implementation of mitigation measures. The residual impacts in all cases are considered to be acceptable however this relies on the mitigation measures being satisfactorily implemented.

Table 3-1: Project Risk Mitigation Matrix

| Without mitigation |  |  |  |  |  |  |  | With mitigation |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk | Extent | Intensity | Duration | Consequence | Probability | Significance | Confidence | Mitigation measures: | Extent | Intensity | Duration | Consequence | Probability | Significance |
| Worker/ public exposure to asbestos during construction ESMP Section 6.1 | Local 1 | High 3 | Long Term 3 | Major 7 | Improbable | Medium | Moderate | - Facility Designers determine presence of asbestos on facilities for renovation/demolition - Where screening shows actual or suspected asbestos-containing-material or lead-based paint residue, construction works will not proceed without agreement from the CIU Safeguards Advisor on appropriate remediation measures based on screening and response protocols - Mitigation measures implemented & checked | Local 1 | Low 1 | Short Term 1 | Minor 3 | Improbable | Very low |
| Worker/ public exposure to lead-based paint residue during construction ESMP Section 6.2 | Local 1 | High 3 | Long Term 3 | Major 7 | Improbable | Medium | Moderate |  | Local 1 | Low 1 | Short Term 1 | Minor 3 | Improbable | Very low |
| Unauthorized land access or land acquisition ESMP Section 7.10 | Wider catch- ment 2 | Med 2 | Long Term 3 | Major 7 | Improbable | Medium | High | - Project activities will be consistent with activities authorized under the lease for that land. - Only existing PSS, NTC or CMI leasehold land will be used for project activities. | Local 1 | Low 1 | Short Term 1 | Minor 3 | Improbable | Very low |
| Community health and safety during construction ESMP Section 7.11 | Local 1 | Med 2 | Medium Term 2 | Moderate 5 | Possible | Medium | High | - Construction works undertaken in accordance with Checklist in Section 7.5.1 of this ESMP; - Construction contracts to include matters set out in Section 9. - Bid documents/contracts require contractor to implement all reasonable precautions to prevent accidents and injuries to staff and workers and protect the health and safety of the community - Contractor implements Worker Health and Safety Management Plan in accordance with the guidelines in Annex 2. | Local 1 | Low 1 | Short Term 1 | Minor 3 | Possible | Very Low |
| Worker Health and Safety ESMP Section 7.11.3 | Local 1 | Med 2 | Long Term 3 | Moderate 6 | Probable | Medium | High |  | Local 1 | Low 1 | Med. Term 2 | Minor 4 | Probable | Low |
| Waste Management ESMP Section 6.3 | Wider catch- ment 2 | Med 2 | Medium Term 2 | Moderate 6 | Highly probable | Medium | High | Specific waste mitigation options include: - Design to minimise waste generation. - Capacity building of contractors. - Contractor ensures all construction waste recycled or re-used as far as practicable at all construction locations. - Contractor manages all residual waste. - All residual waste from Wotje, Jaluit and Ebeye taken back to Majuro to be further recycled or re-used (f practicable) or exported from RMI to an authorized recycling or disposal location. - Storage of hazardous materials (e.g. fuels) in bunded/secure enclosures. - Contractor to provide evidence of satisfactory waste management and disposal | Local 1 | Med 2 | Med. term 2 | Mod 5 | Possible | Low |
| Water-related impacts ESMP Section 6.4 | Wider catch- ment 2 | Low 1 | Medium term 2 | Moderate 5 | Probable | Medium | Medium | - Building designs to include rainwater capture and waste minimization features. - Each facility develops drought contingency plan in respect of water supply. - Septic tanks are installed in accordance with EPA administered Toilet Facilities and Sewage Disposal Regulations 1990. - No disposal of wastewater other than to septic tanks. Any other wastewater to be neutralized and managed pursuant to RMIEPA requirements. | Local 1 | Low 1 | Short- term 1 | Minor 3 | Possible | Very Low |
| Vegetation damage ESMP Section 6.5 | Island 3 | Medium 2 | Long Term 2 | Major 7 | Possible | Medium | High | - Wherever possible roots to be left intact and excavation re-routed to avoid damage. - Replanting to be undertaken in some circumstances. - Where practicable replacement will be on a like-for-like basis | Local 1 | Low 1 | Short Term 1 | Minor 3 | Possible | Very Low |
| Construction immediately adjacent to coastal area ESMP Section 6.6 | Wider catch- ment 2 | Medium 2 | Medium Term 2 | Moderate 6 | Possible | Low | Medium | - Design features incorporate climate change/sea level rise resilience - No works undertaken below high tide level | Local 1 | Low 1 | Medium term 2 | Minor 4 | Possible | Very Low |
| Source of Aggregate for Construction ESMP Section 6.9 | Wider catch- ment 2 | Medium 2 | Long Term 3 | Major 7 | Possible | Medium | Medium | - Design will consider resource efficiency for aggregate use. - All aggregates and sands etc. for making concrete will be sourced from overseas. - No locally sourced aggregates or sands etc. will be used; Recycled aggregates may be used | Local 1 | Low 1 | Short term 1 | Minor 3 | Improbable | Very Low |
| Ensuring Safety in the Delivery of After-School Tutoring and Summer School Classes ESMP Section 7.2 | Wider catch- ment 2 | High 3 | Med. term 2 | Major 7 | Probable | High | High | When selecting locations for after school and summer school programs consideration should be given to ensuring: - There is appropriate lighting, both within the classroom and in external areas; - There are windows and doors that allow visibility to classrooms, teacher’s offices and other spaces; - All trainers and other personnel in conduct with students and receive appropriate awareness training on safeguard issues, recognizing abuse and how to make safe and effective referrals - All trainers and other personnel in conduct with students sign Codes of Conduct; - There are age-separated classes or additional supervision in combined age group settings; - There is access to safe and appropriate transportation for attendees to and from after school or summer school programs. Depending on the specific location of the program and existing infrastructure and resources, this could involve organizing a human school bus, ensuring the programs are held in areas accessible by public transport, linking to private transportation options or utilizing existing school buses/mini vans with licensed and trained drivers. | Local 1 | Med 2 | Med. term 2 | Moderate 5 | Possible | Low |
| Purchase computers to equip computer labs ESMP Section 7.3 | Wider catchment 2 | High 3 | Med. term 2 | Major 7 | Probable | High | High | - Ensure school personnel have the appropriate skills to prevent and respond to online SEAH through training and provision of guidelines - Purchase and installation of child safe software and other safeguards to block inappropriate violent and sexual content. | Local 1 | Med 2 | Med. term 2 | Moderate 5 | Possible | Low |
| Teacher Training and Awareness on Social Safeguards ESMP Section 7.4 | Wider catchment 2 | High 3 | Med. term 2 | Major 7 | Probable | High | High | - Ensure teacher and TVET trainers, tutors, mentors and supervisor receive training on recognizing, reporting and making referring in cases of suspected child abuse, SEAH and GBV; strategies to support victims of SEAH and GBV to the extent possible and have functional understanding of PSS and project social safeguards. | Local 1 | Med 2 | Med. term 2 | Moderate 5 | Possible | Low |
| Civil works – Construction of Training Facilities., Dormitories and NTC Facilities in Ebeye and Majuro. ESMP Section 7.5.1 | Wider catch-ment 2 | High 3 | Med. term 2 | Major 7 | Probable | High | High | - The Project will implement a checklist system within the grant monitoring and reporting process that specifies design features to address wide range of risk areas (refer to Section 7.5.1) | Local 1 | Med 2 | Med. term 2 | Moderate 5 | Possible | Low |
| Construction of Dormitories ESMP Section 7.5.2 | Wider catch-ment 2 | High 3 | Med. term 2 | Major 7 | Probable | High | High | - Conduct physical safety audits of dormitories and boarding facilities; - Consult with police, community and church leaders, teachers, parents and students about their perceptions of safety in schools and dormitories, and what needs to be in place for peace of mind; - Ensure there are appropriate school and boarding facility reporting mechanisms in place, aligned with MOEST and GoRMI child protection policies and procedures and that teacher, supervisors and other employees within boarding facilities and summer school programs have received appropriate training to understand and recognize abuse and are able to make safe and effective referrals. | Local 1 | Med 2 | Med. term 2 | Moderate5 | Possible | Low |
| Upgrade NTC’s facilities in Majuro and Ebeye (ESMP Section 7.5.3) | Wider catchment 2 | High 3 | Med. term 2 | Major 7 | Probable | High | High | - Develop and apply a safeguard checklist (similar to the one referred to in Section 7.5.1) to ensure that there is minimal disruption to NTC employees and clients. - Ensure facility design considers safety and accessibility factors, including providing safe spaces, appropriately sized WASH facilities, and physical access for people with disabilities, and proper lighting and security, especially for after-hour training and management support services. | Local 1 | Med 2 | Med. term 2 | Moderate 5 | Possible | Low |
| Grants to TVET Providers (ESMP Section 7.5) | Wider catch- ment 2 | High 3 | Med. term 2 | Major 7 | Probable | High | High | - Ensure school administrators, teachers, and career counsellors have a good understanding of issues related to GBV and SEAH and maintain a watching-presence during construction - Report any possible misconduct immediately following established protocols - communities and parents are well informed about upcoming works and the presence of workers from other locations | Local 1 | Med 2 | Med. term 2 | Moderate 5 | Possible | Low |
| Payment of Stipends to Trainees, Childcare Services; and Subsidies to Interns (ESMP Section 7.7) | Wider catchment 2 | High 3 | Med. term 2 | Major 7 | Probable | High | High | - Ensure appropriate oversight in the selection of trainees, such as utilizing a panel or two-tier selection process, in conjunction with ensuring there are clear guidelines on relationships between trainees and supervisors, as well as appropriate reporting mechanisms for incidents of SEAH or other grievances. This will require development of clear communication guidelines and protocols as specified in the SEP. | Local 1 | Med 2 | Med. term 2 | Moderate 5 | Possible | Low |
| Engagement of PIU Team Members (ESMP Section 7.10) | Wider catchment 2 | High 3 | Med. term 2 | Major 7 | Probable | High | High | - Proper reference and police checks, completion of a SEAH declaration and signing a Code of Conduct. Staff training on SEAH will be mandatory. | Local 1 | Med 2 | Med. term 2 | Moderate 5 | Possible | Low |

World Bank (WB) Report No: ESRSC01042, dated 03/10/2020 |

As set out in the Project Environmental and Social Review Summary (ESRS)

SPREP (2015) “Survey of the Regional Distribution and Status of Asbestos-Contaminated Construction Material and Waste - Best Practice Options for its Management in Pacific Island Countries. Report for the Republic of the Marshall Islands”.  May 2015

For example based around Department of Works (DoW) (2016) Safe Traffic Control at Road Works: Field Guide. Available from www.works.gov.pg.

Guidance on preparing a traffic management plan is available from DoW (2016) Safe Traffic Control at Road Works Available from www.works.gov.pg.

Such as the “Multisectoral Early Childhood Development (ECD) program”

Certain information from the SEP is included in this ESMP for context.  In the event of any discrepancies in wording between the SEP and the ESMP, the wording of the SEP will prevail.