TERMS OF REFERENCE AND SCOPE OF SERVICES

Republic of the Marshall Islands

Ministry of Finance

Terms of Reference

Consulting Firm

| Title: | Public Procurement Business Process Review and Electronic Government Procurement Readiness Assessment |
| --- | --- |
| Location: | Ministry of Finance, Banking & Postal Services, Republic of the Marshall Islands |
| Duration: | 6 to 9 months |
| Tentative Start Date: | June 2026 |

- Background

The Government of the Republic of the Marshall Islands (GoRMI), through the Ministry of Finance, Banking & Postal Services (MOFBPS), is implementing the Strengthening Public Financial Management II (PFM II) Project with financing from the World Bank. The Project aims to improve public financial management practices, strengthen institutional capacity, modernize financial management systems, and enhance transparency across government.

A key component of the PFM II Project is strengthening the public procurement function across MOFBPS and line ministries. Under Sub-component 1.2, the Project seeks to enhance GoRMI’s capability to carry out procurement in compliance with the Procurement Code Act 2026 and its forthcoming regulations. This includes developing procurement templates, improving standard procedures, and delivering comprehensive training and capacity-building across government institutions. Under Sub-component 2.2, the Project will introduce procurement automation, including e-tendering, digital alerts to vendors, and procurement statistics integrated with the Financial Management Information System (FMIS). This digitization will improve transparency, efficiency, market participation, and ease of doing business. The planned implementation period for the Project is five years, commencing on 1 July 2025 and completion by September 2030.

As part of this reform process the Government is undertaking diagnostic activities to review existing procurement processes and assess readiness for the introduction of an Electronic Government Procurement system. The Public Procurement Business Process Review will document and analyze current procurement workflows across government entities identify procedural bottlenecks and recommend streamlined and more efficient procurement processes. The Electronic Government Procurement Readiness Assessment will evaluate the legal institutional technical and market environment for the implementation of electronic procurement including governance arrangements information technology infrastructure system integration considerations and supplier readiness.

The assignment will include consultations and workflow review across selected pilot ministries and key government stakeholders involved in procurement, finance, and digital transformation. Initial focus ministries/entities shall include:

- Ministry of Finance, Banking and Postal Services (MOFBPS)

- Ministry of Public Works, Infrastructure and Utilities (MPWIU)

- Ministry of Health and Human Services (MOHHS)

- Ministry of Education, Sports and Training (MEST)

Additional ministries, departments, statutory authorities, or public entities may be included during implementation in consultation with the Client. Given the Government’s broader digital transformation agenda, the assignment shall also be aligned with ongoing digital government initiatives and system modernization efforts, including coordination with Digital RMI and other relevant ICT and digital governance stakeholders.

The Ministry therefore intends to engage a consulting firm to conduct both assignments as an integrated diagnostic exercise. The findings will inform the scope functional requirements and phased implementation approach for the electronic procurement system to be introduced under the PFM II Project.

- Objective of the Assignment

The objective of the assignment is to conduct a Public Procurement Business Process Review and an Electronic Government Procurement Readiness Assessment to support procurement reform and inform the design functional scope and phased implementation approach for an electronic procurement system in the Republic of the Marshall Islands.

- Outline of Tasks and Responsibilities

The consulting firm will undertake a comprehensive diagnostic covering procurement processes institutional governance legal frameworks information technology infrastructure and supplier readiness relevant to electronic procurement implementation.

The assignment will include the following main tasks.

Task 1 Conduct procurement business process review

The consulting firm shall undertake business process mapping and procurement workflow assessment across the Ministry of Finance, Banking and Postal Services and a selected sample of key procuring entities.

The review shall include, at a minimum, the Ministry of Finance, Banking and Postal Services, the Ministry of Health and Human Services, the Ministry of Education, Sports and Training, and the Ministry of Public Works, Infrastructure and Utilities. The review will include:

- Review procurement procedures currently applied across selected ministries and agencies.

- Document procurement workflows covering procurement planning solicitation evaluation contract award and contract management.

- Identify bottlenecks procedural inefficiencies administrative delays and institutional constraints affecting procurement performance.

- Prepare visual process maps illustrating current procurement workflows.

- Assess the practical alignment of current procurement practices with the Procurement Code Act 2026 and relevant regulations.

- Develop recommended future state procurement workflows and process models.

- Provide recommendations to inform improvements in procurement procedures and operational practices.

Task 2 Review legal and regulatory environment for electronic procurement

- Conduct a high level review of the existing legal and regulatory framework to confirm that the current framework adequately supports electronic procurement implementation and to identify any practical procedural, regulatory, or implementation issues that may need clarification.

- Identify any practical legal, procedural, or regulatory measures required to support operationalization of electronic procurement in line with the Procurement Code Act 2026.

Task 3 Assess institutional governance arrangements

- Review institutional responsibilities for procurement oversight and system management including

- Ministry of Finance, Banking and Postal Services

- Office of Procurement and Supply

- Chief Procurement Officer

- Bid Committee

- Procuring entities

- Selected pilot ministries including the Ministry of Health and Human Services, the Ministry of Education, Sports and Training, and the Ministry of Public Works, Infrastructure and Utilities

- Assess potential governance arrangements for the operation and administration of an electronic procurement system including system ownership administration and oversight responsibilities.

- The assessment shall also examine decision making structures, approval roles, institutional accountability, and user ownership arrangements that may affect the future operation and governance of an electronic procurement system.

Task 4 Assess information technology environment

The consulting firm will assess the information and communication technology environment relevant to electronic procurement implementation. This will include:

- Reviewing infrastructure capacity, connectivity, and system reliability

- Assessing hosting options including government hosted, cloud, or hybrid solutions

- Reviewing cybersecurity considerations and data management practices

- Assessing availability of technical support and system maintenance capacity

- Coordinating with Digital RMI and other relevant government ICT stakeholders to ensure that recommendations for the electronic procurement system are aligned with national digital architecture, hosting arrangements, interoperability standards, cybersecurity requirements, and broader government digital integration priorities.

Task 5 Assess potential integration with financial management systems

- Assess the current Financial Management Information System environment and identify potential integration points between procurement processes and financial management systems including

- procurement planning and budget controls

- contract registration

- commitment management

- procurement reporting

- Provide recommendations on possible integration approaches for future phases.

- This task shall also consider integration implications with other relevant government digital platforms and systems, in consultation with Digital RMI and other relevant stakeholders where appropriate.

Task 6 Assess supplier and market readiness

- Assess the capacity of suppliers contractors and service providers to participate in electronic procurement processes.

- Review factors such as

- digital literacy among suppliers

- internet access and infrastructure

- existing procurement participation practices

- potential barriers to adoption of electronic bidding systems

- Recommend measures to support supplier participation including training outreach and guidance materials.

Task 7 Provide recommendations for electronic procurement system development

- Based on the assessment findings provide recommendations on the functional scope and key modules of the electronic procurement system including

- supplier registration

- procurement planning

- tender publication

- electronic bid submission

- evaluation workflow management

- contract registration and reporting

- Provide recommendations on a phased implementation approach aligned with the institutional capacity and procurement environment of the Republic of the Marshall Islands.

- The consultant should also provide high level functional requirements and system architecture considerations to guide the future procurement of an electronic procurement platform.

Methodology

The consulting firm shall propose a methodology for conducting the assessment including stakeholder consultations document review workshops and validation sessions.

The methodology should ensure participation of key ministries, procurement officers, ICT units, Digital RMI, and private sector representatives.

The methodology should also include structured consultations with the selected pilot ministries and entities covered under the business process review, and a practical approach to validating workflow findings and future state recommendations with relevant government stakeholders.

The methodology should include review of legal and regulatory provisions relevant to electronic procurement and consultation with relevant government stakeholders where required.

- Deliverables and Payment Terms

| Deliverable | Description | Key Contents | Timeline from Contract Start | Payment |
| --- | --- | --- | --- | --- |
| Inception Report | The report will present the consultant’s understanding of the assignment and the proposed methodology for conducting the Business Process Review and the Electronic Government Procurement Readiness Assessment. It will include the work plan stakeholder consultation approach and reporting arrangements. | - Assignment methodology and analytical framework. Detailed work plan and implementation schedule. - Stakeholder consultation plan including ministries agencies and private sector suppliers. - Data collection approach including document review and interviews. Outline of deliverables reporting structure and validation process. | Week 2 | 15 percent |
| Business Process Review Report | Documentation and analysis of current procurement workflows across selected ministries and agencies, including identification of bottlenecks, inefficiencies, administrative delays, and alignment with the Procurement Code Act 2026. | - Mapping of procurement processes including procurement planning solicitation evaluation contract award and contract management. - Visual workflow diagrams of current procurement processes. - Analysis of operational bottlenecks and approval delays. Assessment of alignment between current practices and the Procurement Code Act 2026. - Identification of areas requiring process simplification or reform. | Month 3 | 25 percent |
| Institutional and ICT Readiness Assessment Report | Diagnostic assessment of the institutional and technical environment required to support the implementation of electronic government procurement. | - Assessment of institutional roles governance arrangements and oversight structures. - Review of ICT infrastructure connectivity hosting options data management and cybersecurity considerations. - Assessment of potential integration with the Financial Management Information System and other government systems. - Identification of any practical legal or procedural considerations relevant to implementation | Month 4 | 25 percent |
| Draft Integrated Assessment Report | Consolidated draft report presenting findings from the Business Process Review and Electronic Government Procurement Readiness Assessment together with preliminary recommendations for procurement process improvements and system development. | - Integrated analysis of procurement processes legal framework institutional capacity ICT readiness and supplier readiness. - Recommended future state procurement workflows. - Preliminary functional requirements and proposed modules for the electronic procurement platform. Identification of risks constraints and implementation considerations. | Month 5 | 20 percent |
| Final Integrated Assessment Report and Presentation | Final report incorporating comments from the Ministry of Finance Banking and Postal Services and other stakeholders. The consultant will present the final findings and recommendations during a validation workshop. In addition to the final report, the consultant shall provide stakeholder friendly communication outputs to support understanding and validation of findings and recommendations. These may include a concise presentation deck, infographic style summary materials, visual process maps, and where feasible and appropriate, a short visual explainer, narrated walkthrough, or other digital summary product to illustrate the proposed future state procurement processes and electronic procurement transition pathway. | - Final procurement workflow models and process improvement recommendations. - Final electronic procurement readiness assessment findings. - Recommended functional architecture governance arrangements and phased implementation roadmap for the electronic procurement platform. - Presentation of findings and recommendations to government stakeholders. - Visual communication materials suitable for both technical and non-technical audiences | Month 6 | 15 percent |

Note: Timeline is indicative and may be adjusted in consultation with the Ministry based on scope and implementation progress.

All deliverables will be submitted in English in electronic format and will be subject to review and approval by the Ministry of Finance Banking and Postal Services prior to payment.

- Duration and Level of Effort

The assignment will be carried out over a period of approximately six to nine months. The level of effort will be intermittent and distributed across this period, with a combination of remote work and in country missions.

The consulting firm is expected to mobilize a team of specialists to undertake the work during this period. The duration may be adjusted in consultation with the Ministry depending on the scope and progress of the assignment.

- Reporting Requirements

The consulting firm will work under the supervision of the PFM II Project Manager at the Ministry of Finance Banking and Postal Services.

The consulting firm will work closely with the Chief Procurement Officer, government information technology units, Digital RMI, procurement officers in selected line ministries, and the PFM II Project Team. Coordination with relevant government entities will be necessary to ensure that the assessment reflects the operational realities of procurement practices across government institutions.

The consulting firm will conduct consultations with key stakeholders including the Office of Procurement and Supply information technology units financial management teams and representatives of suppliers where appropriate. These consultations will support the collection of information required for the Business Process Review and the Electronic Government Procurement Readiness Assessment.

The consulting firm will review relevant project documentation including the Procurement Code Act 2026 procurement regulations standard procurement documents the EGP Reform Roadmap the Financial Management Information System environment and other relevant public financial management policies.

All reports and deliverables will be prepared in English and submitted in electronic format. Printed copies will be provided if requested by the Ministry of Finance Banking and Postal Services.

The consulting firm will provide periodic progress updates to the PFM II Project Manager during the assignment. The firm will promptly notify the Ministry of any issues that may affect the scope timeline or delivery of the assignment.

All deliverables will be submitted to the Ministry of Finance Banking and Postal Services for review and approval. The Ministry will provide consolidated comments and feedback and the consulting firm will revise the reports accordingly before final submission.

The consulting firm will also deliver a presentation summarizing the key findings and recommendations of the assignment during a validation meeting with relevant government stakeholders.

- Required Qualifications and Experience

The consulting firm should demonstrate substantial experience in public procurement reform electronic procurement systems and public financial management modernization preferably in government or public sector environments.

The firm should demonstrate experience in

- conducting procurement diagnostics and business process reviews in the public sector

- assessing electronic procurement readiness or designing electronic procurement systems

- public procurement policy development and institutional strengthening

- financial management systems including integration with financial management information systems

- working with government institutions in developing country contexts

- experience with World Bank or other multilateral development bank funded projects will be an advantage

Key Experts

The consulting firm should propose a team of qualified experts with experience relevant to the scope of the assignment. The firm may propose additional or alternative experts as appropriate to the scope of the assignment. Experience in small island states or similar public administration contexts and in practical implementation of procurement reforms will be an advantage.

The team may include the following key specialists.

- Team Leader
Extensive experience in public procurement reform procurement diagnostics, institutional strengthening. Demonstrated ability to lead multi stakeholder engagement and deliver complex advisory assignments. At least ten years experience. Experience in reviewing procurement legal and regulatory frameworks and advising on alignment with electronic procurement is required. The Team Leader will coordinate legal, institutional, and technical aspects of the assignment.

- Electronic Procurement Specialist
Experience in the design, implementation, or assessment of electronic procurement systems and digital procurement platforms. At least six years of relevant experience in e procurement systems. Experience in defining functional requirements, procurement workflows, and system modules such as supplier registration, tender management, electronic bid submission, and evaluation workflows. Familiarity with public sector procurement reform and integration with financial management systems will be an advantage.

- Information Technology Specialist
Experience in assessing information technology environments, system architecture, hosting options, and integration with financial management systems. Experience in evaluating infrastructure capacity, cybersecurity considerations, and system reliability in public sector contexts. Familiarity with cloud based and government hosted solutions and system interoperability will be an advantage.

- Facilities to be Provided by the Client

The Ministry of Finance Banking and Postal Services will facilitate access to relevant government stakeholders, including ministries, procurement units, and information technology teams. The Ministry will provide access to available procurement legislation, regulations, standard documents, and other relevant materials required for the assignment.

The Ministry will support coordination of meetings, workshops, and consultations. Where required, reasonable workspace and logistical support may be provided during in country missions.

- Travel Arrangements

The assignment may require travel to the Republic of the Marshall Islands to conduct stakeholder consultations meetings with government entities and presentations of findings to relevant stakeholders.

The consultant may be required to undertake up to two missions to Majuro during the course of the assignment. Each mission may involve one or more team members as agreed with the Ministry. Part of the assignment may be carried out remotely including document review data analysis and virtual consultations with government stakeholders where appropriate.

All travel costs including international airfare local transportation accommodation and daily subsistence allowance will be reimbursed in accordance with the applicable policies of the Strengthening Public Financial Management II Project and the World Bank Procurement Regulations. Travel arrangements will be coordinated in consultation with the PFM II Project Management Office.

Annex -1 Cover Letter Template

Date

To
PFM II Project Manager
Ministry of Finance Banking and Postal Services
Republic of the Marshall Islands

Subject: Expression of Interest for Consulting Services

Dear Sir,

We the undersigned consulting firm hereby express our interest in providing consulting services for the assignment Public Procurement Business Process Review and Electronic Government Procurement Readiness Assessment for the Ministry of Finance Banking and Postal Services under the Strengthening Public Financial Management II Project.

We confirm our interest in undertaking this assignment and confirm that our firm has the relevant experience and technical expertise in public procurement reform electronic procurement systems and public sector institutional strengthening.

We confirm that our firm is eligible to participate in this procurement process and that there are no conflicts of interest that would prevent us from undertaking this assignment.

Please find attached our Expression of Interest including firm profile relevant experience and supporting documentation.

We appreciate the opportunity to submit our Expression of Interest and look forward to the possibility of being shortlisted for this assignment.

Sincerely

Name
Position
Consulting Firm
Address

Annex -2 Application Form – Expression of Interest

# APPLICATION FORM – EXPRESSION OF INTEREST

Assignment Title: Public Procurement Business Process Review and Electronic Government Procurement Readiness Assessment

Project: Strengthening Public Financial Management II Project

| Section 1 – Firm Information |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Firm Name |  |  |  |  |  |  |  |  |  |
| Country of Registration |  |  |  |  |  |  |  |  |  |
| Year Established |  |  |  |  |  |  |  |  |  |
| Legal Status of the Firm |  |  |  |  |  |  |  |  |  |
| Registered Address |  |  |  |  |  |  |  |  |  |
| Telephone |  |  |  |  |  |  |  |  |  |
| Email |  |  |  |  |  |  |  |  |  |
| Website |  |  |  |  |  |  |  |  |  |
| Name of authorized representative |  |  |  |  |  |  |  |  |  |
| Contact Person for this Assignment Name Position Telephone Email |  |  |  |  |  |  |  |  |  |
| Section 2 – Brief Description of the Firm Provide a brief description of the consulting firm including its areas of expertise organizational structure and relevant experience in public procurement reform electronic procurement systems and public financial management projects. |  |  |  |  |  |  |  |  |  |
| Section 3 – Relevant Experience of the Firm Provide details of up to five assignments undertaken during the past ten years that demonstrate the firm’s experience relevant to this assignment |  |  |  |  |  |  |  |  |  |
| Project title | Client Organization |  | Country |  | Year Completed |  | Scope of Work |  | Relevance to This Assignment |
| Section 4 – Technical and Managerial Capacity Describe the firm’s technical and managerial capacity to undertake the assignment. |  |  |  |  |  |  |  |  |  |
| Section 5 – Availability of Key Experts |  |  |  |  |  |  |  |  |  |
| Expert Role |  | Name |  |  |  | Years of Experience |  | Area of Expertise | Relevant Experience Summary |
| Team Leader – Public Procurement Specialist |  |  |  |  |  |  |  |  |  |
| Electronic Procurement Specialist |  |  |  |  |  |  |  |  |  |
| Information Technology Specialist |  |  |  |  |  |  |  |  |  |
| Section 6 – Response to Evaluation Criteria |  |  |  |  |  |  |  |  |  |
| 6.1 Experience conducting public procurement diagnostics or procurement reform assignments |  |  |  |  |  |  |  |  |  |
| 6.2 Experience in electronic procurement systems or digital procurement initiatives |  |  |  |  |  |  |  |  |  |
| 6.3 Experience working with public financial management systems including FMIS integration |  |  |  |  |  |  |  |  |  |
| 6.4 Experience supporting government institutions in developing country contexts |  |  |  |  |  |  |  |  |  |
| 6.5 Experience with World Bank or other multilateral development bank financed projects |  |  |  |  |  |  |  |  |  |
| Section 7 – Declaration We certify that the information provided in this Expression of Interest is true and correct to the best of our knowledge. |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  |  |  |
| Position |  |  |  |  |  |  |  |  |  |
| Consulting Firm |  |  |  |  |  |  |  |  |  |
| Signature |  |  |  |  |  |  |  |  |  |
| Date |  |  |  |  |  |  |  |  |  |

Annex -3 Conflict of Interest Declaration Form

Assignment Title: Public Procurement Business Process Review and Electronic Government Procurement Readiness Assessment

Consulting Firm Name

We hereby declare that our firm and its affiliates do not have any conflict of interest in relation to this assignment in accordance with paragraphs 3.14, 3.16 and 3.17 of the World Bank Procurement Regulations for IPF Borrowers.

We confirm that

our firm has no financial or personal relationships that could improperly influence the performance of this assignment

our firm has not been involved in preparing the Terms of Reference for this assignment in a manner that would create a conflict of interest

our firm will disclose any potential conflict of interest that may arise during the procurement process or contract implementation

Authorized Representative

Name
Position
Consulting Firm

Signature
Date